## Parts
Item | Price | Vendor | Received | Paid | Plan_Timing | Plan_Decision | Inventory_Group | Restore_Replace | Build_State | Reconciled_Status | Reconciled_Note | Procured_Mark | Estimate_Range_PKR | Estimate_Avg_PKR | Estimate_Priority | Estimate_Source | Source_Tab | Source_Row | Inventory_ID | Purchase_Priority | Priority_Order | Priority_Basis | New_vs_Refresh_Decision | Photo_Evidence_Level | Photo_Evidence_Basis | Decision_Confidence | Lead_Time_Risk | Sourcing_Region
Rubber grommet set |  | Use local electrical markets first; avoid duplicate online orders. | Needs check | 9200 COD (ref Wiring) | in_flight_now | track_in_flight_order | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Already ordered/in-flight in procurement and mirrored by Wiring grommet entry; avoid duplicate buy. ¦ RR action=Use local electrical markets first; avoid duplicate online orders.; evidence=Already ordered; do not rebuy. | ordered/in-flight |  |  |  |  | Parts | 35 | INV-0034 | P1 - In flight / immediate | 1 | procurement_pass2 | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Schneider Harmony 22mm 2-position maintained selector switch (1NO, black) x 4 | 31900 | purchaser.com.pk ¦ https://purchaser.com.pk/schneider-harmony-22mm-push-button-2-position-selector-switch-black-maintained-1-no-600-v/ | No | Ordered (combined total) | in_flight_now | track_in_flight_order | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Combined order total PKR 31,900 for both selector lines (4x 2-position + 3x 3-position); awaiting delivery. | ordered/in-flight |  |  |  |  | Parts | 38 | INV-0037 | P1 - In flight / immediate | 1 | decision_or_timing | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Schneider Harmony XB4 22mm 3-position maintained selector switch (2NO, long handle) x 3 |  | purchaser.com.pk ¦ https://purchaser.com.pk/schneider-selector-switch-harmony-xb4-metal-black-22mm-long-handle-3positions-stay-put-2no/ | No | Included in combined total | in_flight_now | track_in_flight_order | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Price included in PKR 31,900 combined selector-switch order total logged on 2-position row. | ordered/in-flight |  |  |  |  | Parts | 39 | INV-0038 | P1 - In flight / immediate | 1 | decision_or_timing | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Body mount shims/spacers alignment pack |  | Local machine shop / MTL washer stock | No | Ordered (Millat, not yet paid) | pre_tub_refit | prepare_before_trial_fit | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Active required purchase item from Procurement_Pass2. ¦ Tub refit locked to original OEM mount locations; no custom offset mounting. ¦ P2 active batch confirmed 2026-04-15 ¦ Reconciled 2026-04-17: no single retail shim kit was reliable locally; build the thickness stack from washer stock after measuring the body-mount gaps. ¦ Price basis 2026-04-15: alignment shim pack assorted thicknesses for tub leveling. ¦ Local Pakistan shim stack options found: MTL washer stock plus spacer/plate-spacer if a rigid block is needed. ¦ Millat shim stock ordered: M12 flat washers x40, M8 flat washers x20, plate-spacer x4. Not yet paid. | ordered/in-flight | 3000-12000 | 7000 | Medium | https://parts.millat.com.pk/product/washer-flat-m12/ ; https://parts.millat.com.pk/product/washer-flat-m8/ ; https://parts.millat.com.pk/product/plate-spacer/ ; local machine-shop cut spacer stack | Parts | 13 | INV-0012 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_preferred
Body-to-chassis mount rubber kit |  | Walton Toyota |  |  | pre_tub_refit | quote_at_walton_toyota | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Active required purchase item from Procurement_Pass2. ¦ Tub refit locked to original OEM mount locations; no custom offset mounting. ¦ P2 active batch confirmed 2026-04-15 ¦ Reconciled 2026-04-17: quote-by-dimensions/custom-molded route preferred; verify sleeve fit, hardness and exact mount count against the chassis before payment. ¦ Price basis 2026-04-15: body mount rubber set, local pattern if correct hardness and sleeve fit verified. ¦ Age/condition rule: NEW_ONLY body mount rubbers/sleeves. ¦ Pending quotation at Walton Toyota. Compare genuine Toyota quote against local custom-molded fallback if needed. | Q | 15000-60000 | 30000 | High | Walton Toyota quote | Parts | 12 | INV-0011 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_preferred
Cowl body mounting shim sub-assy (52032-90300) |  | Walton Toyota |  |  | pre_tub_refit | quote_at_walton_toyota | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Toyota GR Heritage lists 52032-90300 as cowl body mounting shim sub-assy for BJ4#, FJ4# (6903-7902). Pending quotation at Walton Toyota. | Q |  |  |  | Toyota GR Heritage / Walton Toyota quote | Parts | 14 | INV-0256 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-17) | NEW_ONLY | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_preferred
Dashboard fascia / auxiliary switch panel (if OEM holes are insufficient) |  | Pakwheels fabrication shops: https://www.pakwheels.com/accessories-spare-parts/search/-/q_fabrication+shop+lahore/ ¦ OLX fabrication: https://www.olx.com.pk/items/q-automotive-fabrication | No |  | pre_dash_refit | fabricate_only_if_required_by_switch_fitup | replacement_part | replace_or_procure | cancelled | cancelled | Only buy/fabricate if right+mid cluster hole count/spacing/depth cannot safely host all required controls. ¦ P2 active batch confirmed 2026-04-15 ¦ Reconciled 2026-04-15: fabricate only if OEM holes cannot safely fit required controls. ¦ Not required: dash hole layout is sufficient for the planned controls. | cancelled | 5000-30000 | 15000 |  | https://www.pakwheels.com/accessories-spare-parts/search/-/q_fabrication+shop+lahore/ ; https://www.olx.com.pk/items/q-automotive-fabrication | Parts | 40 | INV-0039 | P2 - Buy before refit | 6 | P2-E conditional fabrication only if switch fit requires it (2026-04-15) | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Electrical power steering |  | Pakwheels Vitz EPS column: https://www.pakwheels.com/accessories-spare-parts/search/-/q_vitz+eps+column/ ¦ Pakwheels Vitz EPS computer: https://www.pakwheels.com/accessories-spare-parts/search/-/q_vitz+eps+computer/ |  |  | pre_tub_refit | buy_complete_eps_column_kit_bilal_ganj_with_inclusion_checklist | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Legacy planned item retained; EPS path remains in scope. ¦ P2 active batch confirmed 2026-04-15 ¦ EPS kit must include at minimum: column-assist EPS unit (motor + torque sensor + reduction gear), EPS controller/ECU or integrated control module, matching connectors with pigtails >=150mm, upper+lower intermediate shaft sections with U-joints, steering coupler/spline adapters for FJ40-side fitment, column mount/clamp bracket set + firewall support bracket, heavy feed cable path for 60A fused supply + ignition trigger lead, fail-safe manual steering capability if assist disabled. Bench-test before payment; reject noisy/jerky units or excessive lash. ¦ Age/condition rule: USED_TESTED_OK_MAX_15Y for EPS donor units; bench-test mandatory. ¦ Quote sent 2026-04-17: full Vitz EPS column assembly, matching EPS ECU/controller, full EPS wiring pigtails/connectors, and if available lower output yoke/stub, intermediate shaft/U-joint section, and column mounting clamp/bracket. ¦ Pending quotation via Bilal Ganj. EPS kit still requires donor-column, ECU/controller, pigtails and fitment hardware. | Q | 54000-136000 | 90000 | High | https://www.pakwheels.com/accessories-spare-parts/search/-/q_vitz+eps+column/ ; https://www.pakwheels.com/accessories-spare-parts/search/-/q_vitz+eps+computer/ | Parts | 52 | INV-0051 | P2 - Buy before refit | 5 | P2-D EPS kit procurement with mandatory inclusion checklist (2026-04-15) | USED_TESTED_OK_MAX_15Y | high | photo_group=chassis_underside; group_photo_count=32; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | bilal_ganj_first_then_online_fallback
Fastener Kit A: Tub-to-chassis mounts (OEM positions) - M10/M12 class 8.8 bolts, matching nuts, flat+spring washers, sleeves |  | MTL Parts | No | Ordered (Millat, not yet paid) | pre_tub_refit | buy_local_grade_spec_kit | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Spec qty baseline: M10x1.25 class 8.8 bolts x16, M10 nuts (nyloc + all-metal mix) x24, M10 flat washers x40, M10 spring washers x20, M10 sleeves/spacers x16, M12 class 8.8 bolts x4, M12 nuts x6, M12 flat washers x12, M12 spring washers x6. Buy +20% spares. ¦ P2 active batch confirmed 2026-04-15 ¦ Reconciled 2026-04-17: prioritize as low-risk, locally available buy-first item. ¦ Price basis 2026-04-15: Kit A detailed qty with +20% spares. ¦ Age/condition rule: NEW_ONLY class-marked structural hardware. ¦ Match removed bolt length and pitch against sample hardware during teardown. ¦ Millat fastener cart placed; not yet received or paid. | ordered/in-flight | 15000-35000 | 24000 | High | https://parts.millat.com.pk/product/screw-m10-x20mm/ ; https://parts.millat.com.pk/product/nut-m10/ ; https://parts.millat.com.pk/product/nylon-nut-m10/ ; https://parts.millat.com.pk/product/washer-lock-m10/ ; https://parts.millat.com.pk/product/bolt-m12-l-55/ ; https://parts.millat.com.pk/product/bolt-m12-l-70/ ; https://parts.millat.com.pk/product/nut-m12/ ; https://parts.millat.com.pk/product/washer-flat-m12/ ; https://parts.millat.com.pk/product/screw-12-point-head-m12x1-5-l-70/ | Manual |  | INV-0243 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium | manual_specification_update_2026_04_15 | high | low | local_pk_preferred
Fastener Kit B: Body panel/bracket hardware - M6/M8 class 8.8 flange bolts, nyloc nuts, washers |  | MTL Parts | No | Ordered (Millat, not yet paid) | pre_tub_refit | buy_local_grade_spec_kit | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Spec qty baseline: M6x1.0 class 8.8 bolts (assorted lengths 12/16/20/25mm) x220, M6 nyloc nuts x160, M6 flange nuts x80, M6 flat washers x300, M6 spring washers x140, M8x1.25 class 8.8 bolts (16/20/25/30mm) x120, M8 nyloc nuts x90, M8 flange nuts x40, M8 flat washers x180, M8 spring washers x90. ¦ P2 active batch confirmed 2026-04-15 ¦ Reconciled 2026-04-17: prioritize as low-risk, locally available buy-first item. ¦ Price basis 2026-04-15: Kit B detailed qty with mixed lengths and washers. ¦ Age/condition rule: NEW_ONLY class-marked structural hardware. ¦ Missing M6 20mm / 25mm and M8 25mm lengths, plus the lock-nut and spring-washer top-up, have been split into Royal Hardware quote rows below. ¦ Working split guess from kit ratios: M6 x12=59, M6 x16=51, M6 x20=42, M6 x25=68; M8 x16=42, M8 x20=36, M8 x25=30, M8 x30=12. Remove M8 x45 cart line for this kit. ¦ Millat fastener cart placed; not yet received or paid. | ordered/in-flight | 18000-40000 | 28000 | High | https://parts.millat.com.pk/product/bolt-m6-x-16/ ; https://parts.millat.com.pk/product/screw-m6x16/ ; https://parts.millat.com.pk/product/nut-hex-m6/ ; https://parts.millat.com.pk/product/nut-m8/ ; https://parts.millat.com.pk/product/washer-flat-m6-2/ ; https://parts.millat.com.pk/product/washer-flat-m8/ ; https://parts.millat.com.pk/product/plain-washer-m-8/ ; https://parts.millat.com.pk/product/washer-lock-m6/ ; https://parts.millat.com.pk/product/washer-lock-3-8/ ; https://parts.millat.com.pk/product/bolt-m8-x-40mm/ ; https://parts.millat.com.pk/product/bolt-m8-x-45mm/ | Manual |  | INV-0244 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium | manual_specification_update_2026_04_15 | high | low | local_pk_preferred
M6 x20 hex bolt (Royal Hardware quote) x42 |  | Royal Hardware | No |  | pre_tub_refit | quote_at_royal_hardware | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote requested for class 8.8 metric M6 x20 hex bolts. Ask for zinc-plated finish and confirm head style against removed samples. | Q |  |  | High | Royal Hardware quote request: https://royalhardware.com.pk/product/hexagonal-bolt-din-933-din-931-ansi/ | Manual |  | INV-RH-001 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium |  | high | low | local_pk_or_on_hand ¦ Royal Hardware quote pending
M6 x25 hex bolt (Royal Hardware quote) x68 |  | Royal Hardware | No |  | pre_tub_refit | quote_at_royal_hardware | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote requested for class 8.8 metric M6 x25 hex bolts. Ask for zinc-plated finish and confirm head style against removed samples. | Q |  |  | High | Royal Hardware quote request: https://royalhardware.com.pk/product/hexagonal-bolt-din-933-din-931-ansi/ | Manual |  | INV-RH-002 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium |  | high | low | local_pk_or_on_hand ¦ Royal Hardware quote pending
M8 x25 hex bolt (Royal Hardware quote) x30 |  | Royal Hardware | No |  | pre_tub_refit | quote_at_royal_hardware | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote requested for class 8.8 metric M8 x25 hex bolts. Ask for zinc-plated finish and confirm head style against removed samples. | Q |  |  | High | Royal Hardware quote request: https://royalhardware.com.pk/product/hexagonal-bolt-din-933-din-931-ansi/ | Manual |  | INV-RH-003 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium |  | high | low | local_pk_or_on_hand ¦ Royal Hardware quote pending
M6 nylon lock nut (Royal Hardware quote) x80 |  | Royal Hardware | No |  | pre_tub_refit | quote_at_royal_hardware | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote requested for metric M6 nylon lock nuts. Match thread pitch to the bolts already ordered. | Q |  |  | High | Royal Hardware quote request: https://royalhardware.com.pk/product/nylon-lock-nut-din-985/ | Manual |  | INV-RH-004 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium |  | high | low | local_pk_or_on_hand ¦ Royal Hardware quote pending
M8 nylon lock nut (Royal Hardware quote) x30 |  | Royal Hardware | No |  | pre_tub_refit | quote_at_royal_hardware | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote requested for metric M8 nylon lock nuts. Match thread pitch to the bolts already ordered. | Q |  |  | High | Royal Hardware quote request: https://royalhardware.com.pk/product/nylon-lock-nut-din-985/ | Manual |  | INV-RH-005 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium |  | high | low | local_pk_or_on_hand ¦ Royal Hardware quote pending
M8 spring washer (Royal Hardware quote) x90 |  | Royal Hardware | No |  | pre_tub_refit | quote_at_royal_hardware | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote requested for metric M8 spring washers / lock washers. Use only where a spring washer is correct for the joint. | Q |  |  | High | Royal Hardware quote request: https://royalhardware.com.pk/product/spring-washer-din-127/ | Manual |  | INV-RH-006 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium |  | high | low | local_pk_or_on_hand ¦ Royal Hardware quote pending
M6 weld nuts top-up (local quote) x20 |  | Steel Works PK | No |  | pre_order_audit | quote_at_steel_works_pk | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Quote requested for M6 weld nuts x20. | Q | 7000-18000 | 12000 | Medium | https://steelworkspk.com/products/weld-nuts-manufacturers-in-lahore/ ¦ https://steelworkspk.com/products/star-washers-supplier-in-lahore/ | Parts |  | INV-0245 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium | manual_specification_update_2026_04_15 | high | low | local_pk
Fastener Kit D: Grounding hardware - star/serrated washers M6/M8/M10 + cleaned contact points |  | MTL Parts ¦ local electrical market | No | Ordered (Millat, not yet paid) | pre_tub_refit | buy_local_grade_spec_kit | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Spec qty baseline: M6 star washers x120, M8 star washers x80, M10 star washers x40, serrated flange nuts M6 x40 and M8 x20, conductive anti-corrosion paste 1 tube. Mandatory on chassis/body/electrical ground points after paint removal at contact pads. ¦ P2 active batch confirmed 2026-04-15 ¦ Reconciled 2026-04-17: prioritize as low-risk, locally available buy-first item. ¦ Price basis 2026-04-15: Kit D star/serrated grounding hardware + conductive paste. ¦ Age/condition rule: NEW_ONLY grounding hardware. ¦ Use star/serrated washers and cleaned bare-metal pads on ground points. ¦ Millat fastener cart placed; not yet received or paid. | ordered/in-flight | 5000-12000 | 8000 | Medium | https://parts.millat.com.pk/product/washer-lock-m6/ ; https://parts.millat.com.pk/product/washer-lock-m10/ ; https://parts.millat.com.pk/product/washer-lock-3-8/ ; https://parts.millat.com.pk/product/washer-flat-m6-2/ ; https://parts.millat.com.pk/product/washer-flat-m8/ ; https://parts.millat.com.pk/product/washer-flat-m12/ ; local conductive paste from the electrical market | Manual |  | INV-0246 | P2 - Buy before refit | 2 | P2-A immediate low-risk local procurement (2026-04-15) | NEW_ONLY | medium | manual_specification_update_2026_04_15 | high | low | local_pk_preferred
Ignition lock security fix (bundle quote - matched-key Vitz donor set) |  | Bilal Ganj | No |  | pre_dash_refit | mandatory_security_fix_before_refit | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Bundle quote under Bilal Ganj. Explicit child rows below capture the ignition cylinder + matched keys, front door RH, front door LH, and back door lock cylinder. Same donor preferred. Avoid smart-entry donors unless the lock set is explicitly included. | Q | 4000-25000 | 12000 | High | Bilal Ganj quote pending; Toyota Vitz lock-cylinder set refs: https://toyota.epc-data.com/vitz/SCP10/146566/body/6712/69570/ ; https://toyota.epc-data.com/vitz/scp90/146745/body/6712/69570/ | Parts | 41 | INV-0040 | P2 - Buy before refit | 3 | P2-B security/control completion after parts audit (2026-04-15) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand ¦ Bilal Ganj quote pending for Vitz matched-key donor set; prefer the same donor vehicle as the EPS column if possible.
Ignition switch lock cylinder + matched keys (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | bundle_component_of_matched_key_vitz_set | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Explicit part of the Bilal Ganj Vitz matched-key donor set quote. Same donor preferred. | Q |  |  | High | Quoted as part of the matched-key Vitz donor set; see bundle row above. | Parts | 41 | INV-0040A | P2 - Buy before refit | 3 | P2-B security/control completion after parts audit (2026-04-15) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand ¦ Bilal Ganj quote pending for same donor set
Front door lock cylinder RH (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | bundle_component_of_matched_key_vitz_set | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Explicit part of the Bilal Ganj Vitz matched-key donor set quote. Same donor preferred. | Q |  |  | High | Quoted as part of the matched-key Vitz donor set; see bundle row above. | Parts | 41 | INV-0040B | P2 - Buy before refit | 3 | P2-B security/control completion after parts audit (2026-04-15) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand ¦ Bilal Ganj quote pending for same donor set
Front door lock cylinder LH (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | bundle_component_of_matched_key_vitz_set | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Explicit part of the Bilal Ganj Vitz matched-key donor set quote. Same donor preferred. | Q |  |  | High | Quoted as part of the matched-key Vitz donor set; see bundle row above. | Parts | 41 | INV-0040C | P2 - Buy before refit | 3 | P2-B security/control completion after parts audit (2026-04-15) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand ¦ Bilal Ganj quote pending for same donor set
Back door lock cylinder (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | bundle_component_of_matched_key_vitz_set | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Explicit part of the Bilal Ganj Vitz matched-key donor set quote. Same donor preferred. | Q |  |  | High | Quoted as part of the matched-key Vitz donor set; see bundle row above. | Parts | 41 | INV-0040D | P2 - Buy before refit | 3 | P2-B security/control completion after parts audit (2026-04-15) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand ¦ Bilal Ganj quote pending for same donor set
Internal compact covered blade fuse box (OEM-style) x3 |  | Bilal Ganj |  |  | pre_dash_refit | buy_3_compact_covered_oem_style_fuse_boxes_bilal_ganj_first | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote pending via Bilal Ganj scout. Use compact covered blade-fuse box only; no relays in this cabin box. Keep the OEM-style compact covered format and avoid large open universal blocks. If Bilal Ganj cannot source the exact format, fall back to the verified local OEM-style path rather than importing a universal block. | Q | 11100-21000 | 15000 | High | Bilal Ganj scout / covered OEM-style blade fuse box only | Parts_Estimates | 41 | INV-0203 | P2 - Buy before refit | 3 | P2-B electrical completion (Bilal Ganj first for compact OEM-style fuse boxes) (2026-04-15) | NEW_ONLY | high | electrical_work_completed_except_internal_fuse_boxes | high | low | local_pk
Foam Cell Suspension Kit - Medium (TOY004BKF) x2 |  | IRONMAN 4X4 / Xtreme 4x4 quote |  |  | pre_tub_refit | quote_pending_ironman_suspension | replacement_part | replace_or_procure | planned_or_open | planned_or_open | Quote sent 2026-04-17 to Ironman/Xtreme 4x4; this is now the single suspension path. Ironman catalogue for LC 40/42/46 series shows the TOY004BKF medium kit as the full bundle: leaf springs, shocks, U-bolts, polyurethane bushes, greasable shackles/pins, and steering damper. Do not add separate duplicate hardware unless the supplier breaks the kit into partial line items. | Q | [6 empty] | INV-0258 | P2 - Buy before refit | 2 | P2-C suspension quote request (2026-04-17) | NEW_ONLY | low | quote_email_only | medium | high | pakistan_or_import
12mm split wiring pipe / loom pipe | 10m | Montgomery Road (Lahore) | Y | Y | pre_order_audit | stock_audit_then_local_topup | wiring_material | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | Open item with no procurement evidence yet. ¦ Migrated from Wiring row 62 into Parts inventory. ¦ User reported 8m of loom pipe on hand; top up only if routing shows a shortage. | ✓ |  |  |  |  | Wiring | 62 | INV-0099 | P3 - Audit then buy | 3 | decision_or_timing | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
16mm split wiring pipe / loom pipe | 6m | Montgomery Road (Lahore) | Y | Y | pre_order_audit | stock_audit_then_local_topup | wiring_material | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | Open item with no procurement evidence yet. ¦ Migrated from Wiring row 63 into Parts inventory. ¦ User reported 8m of loom pipe on hand; top up only if routing shows a shortage. | ✓ |  |  |  |  | Wiring | 63 | INV-0100 | P3 - Audit then buy | 3 | decision_or_timing | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
8mm split wiring pipe / loom pipe | 5m | Montgomery Road (Lahore) | Y | Y | pre_order_audit | stock_audit_then_local_topup | wiring_material | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | Open item with no procurement evidence yet. ¦ Migrated from Wiring row 61 into Parts inventory. ¦ User reported 8m of loom pipe on hand; top up only if routing shows a shortage. | ✓ |  |  |  |  | Wiring | 61 | INV-0098 | P3 - Audit then buy | 3 | decision_or_timing | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Electric wires |  |  |  |  | pre_order_audit | stock_audit_then_local_topup | replacement_part | inspect_then_decide | cancelled | cancelled | RR action=Use Montgomery Road / local electrical markets for small top-ups after stock count.; evidence=Workbook shows substantial wiring stock already received/paid; top up only missing sizes/connectors. ¦ Covered by existing wire stock; no standalone generic wire buy required. | cancelled |  |  |  |  | Restore_Replace | 33 | INV-0162 | P3 - Audit then buy | 3 | procurement_pass2 | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Manual fuel-stop switch / hidden kill switch (covered by on-hand 4-switch panel) |  | Universal 4-inch Switch Panel 3pcs (on-hand) | Y | Y | pre_dash_refit | use_on_hand_switch_panel_or_hidden_switch | replacement_part | inspect_then_decide | procured_or_on_hand | covered_by_on_hand_switch_panel | Use one spare position in the already received 4-switch panel if the fuel-stop control is implemented now. Keep the manual diesel cutoff cable as backup. Only source a dedicated concealed latching switch if the panel layout proves unsuitable. | ✓ |  |  |  |  | Parts | 43 | INV-0042 | P3 - Audit then buy | 3 | electrical top-up only after stock audit (2026-04-15) | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
H4 Ceramic Headlight Connector - H4 - High | 550 | autoxpertpakistan | Y | Y | pre_order_audit | stock_audit_then_local_topup | replacement_part | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | Open item with no procurement evidence yet. ¦ Migrated from Wiring row 52 into Parts inventory. ¦ RR action=Use Montgomery Road / local electrical markets for small top-ups after stock count.; evidence=Workbook shows substantial wiring stock already received/paid; top up only missing sizes/connectors. ¦ Duplicate open row closed; covered by the already received H4 connector. | ✓ |  |  |  |  | Wiring | 52 | INV-0094 | P3 - Audit then buy | 3 | procurement_pass2 | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Hazard switch (red latching pushbutton, panel-mount, automotive 12V) |  | electronicstore.pk | Y | Y | pre_order_audit | stock_audit_then_local_topup | wiring_material | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | Marked received per user confirmation. Keep as the hidden/manual fuel-stop / hazard-control option if needed. | ✓ |  |  |  |  | Parts | 129 | INV-0121 | P3 - Audit then buy | 3 | decision_or_timing | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Horn circuit wiring termination (relay already on-hand) |  | Relay box on-hand / steering wheel horn switch | Y | Y | pre_order_audit | wire_existing_relay_box | replacement_part | inspect_then_decide | procured_or_on_hand | covered_by_existing_relay_box | No separate horn part purchase is needed. The horn is already embedded in the steering wheel; route control and power into the existing relay box and terminate the harness ends only. | ✓ |  |  |  |  | Restore_Replace | 35 | INV-0163 | P3 - Audit then buy | 3 | procurement_pass2 | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Hot rod wiring quote |  | On hand / deferred |  |  | pre_order_audit | defer_until_scope_change | replacement_part | inspect_then_decide | cancelled | cancelled | User confirmed this is not needed now; no separate hot-rod wiring order required. | cancelled |  |  |  |  | Restore_Replace | 19 | INV-0151 | P3 - Audit then buy | 3 | not required for current build scope | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Insulated Thimbles Male lug 4mm Yellow in Pakistan × 1 | 800 | On hand | Y | Y | pre_order_audit | use_existing_stock | wiring_material | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | User confirmed there is plenty of yellow ring-type stock already on hand; no more needed for now. | ✓ |  |  |  |  | Wiring | 46 | INV-0088 | P3 - Audit then buy | 3 | covered by existing yellow ring connectors on hand | INSPECT_THEN_DECIDE | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
M6 star / lock washer |  | Steel Works PK |  |  | pre_order_audit | quote_at_steel_works_pk | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Quote requested for M6 star washers x120. | Q |  |  |  | https://steelworkspk.com/products/weld-nuts-manufacturers-in-lahore/ ¦ https://steelworkspk.com/products/star-washers-supplier-in-lahore/ | Parts | 36 | INV-0035 | P3 - Audit then buy | 3 | decision_or_timing | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk
M8 star / lock washer |  | Steel Works PK |  |  | pre_order_audit | quote_at_steel_works_pk | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Quote requested for M8 star washers x80. | Q |  |  |  | https://steelworkspk.com/products/weld-nuts-manufacturers-in-lahore/ ¦ https://steelworkspk.com/products/star-washers-supplier-in-lahore/ | Parts | 37 | INV-0036 | P3 - Audit then buy | 3 | decision_or_timing | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk
PET expandable braided sleeving (100ft 1/4 inch) |  | On hand | Y | Y | pre_order_audit | use_existing_stock | replacement_part | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | User confirmed braided sleeving is already on hand; no more needed yet. | ✓ |  |  |  |  | Restore_Replace | 20 | INV-0152 | P3 - Audit then buy | 3 | covered by existing braided sleeving stock | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Star washers (bite into metal) |  | Steel Works PK |  |  | pre_order_audit | quote_at_steel_works_pk | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Quote requested for M10 star washers x40. | Q |  |  |  | https://steelworkspk.com/products/weld-nuts-manufacturers-in-lahore/ ¦ https://steelworkspk.com/products/star-washers-supplier-in-lahore/ | Restore_Replace | 21 | INV-0153 | P3 - Audit then buy | 3 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk
M-2011 3pin ON-OFF Toggle Switch Single Pole (concealed starter interrupt switch) |  | electronicstore.pk ¦ https://electronicstore.pk/product-tag/m-2011-3pin-on-off-toggle-switch-single-pole/ | No | Y | in_flight_now | track_in_flight_order | replacement_part | replace_or_procure | ordered_in_flight | needs_confirmation | Paid at ElectronicStore for the concealed starter interrupt switch. Use as the hidden ON-OFF control under the dash; relay hardware is already on hand. | ordered/in-flight |  |  |  | https://electronicstore.pk/product/12mm-metal-push-button-switch-anti-vandal-latching-ring-led-white-4-pin-red-led/ | Parts | 42 | INV-0041 | P3 - Audit then buy | 3 | security implementation using existing relay stock first (2026-04-15) | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk
3mm Sound Damping Sheet / Deadening Pad | 29500 | Outsourced sound-deadening installer |  |  | post_rust_repair | outsourced_not_a_purchase | consumable_material | inspect_then_decide | cancelled | cancelled | Cancelled from procurement: sound damping is outsourced rather than bought as a direct parts item. | cancelled |  |  |  |  | Substances | 6 | INV-0126 | P4 - Post inspection | 4 | Body chemistry/insulation gated to tub-off rust/weld findings | INSPECT_THEN_DECIDE | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Accessory belt set |  | Walton Toyota |  |  | post_tub_off_inspection | quote_at_walton_toyota | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ Quote/pending at Walton Toyota. | Q |  |  |  |  | Parts | 17 | INV-0016 | P4 - Post inspection | 4 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Air filter element | 3250 | PakWheels | No | PKR 3,399 (paid incl shipping) | in_flight_now | track_in_flight_order | replacement_part | inspect_then_decide | ordered_in_flight | needs_confirmation | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ PakWheels order placed: Toyota Land Cruiser 1998-2007 Air Filter Super JT 17801-50040. ¦ Item price PKR 3,250 + shipping PKR 149. | ordered/in-flight |  |  |  |  | Parts | 18 | INV-0017 | P4 - Post inspection | 4 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Brake flexible hose set front and rear |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 19 | INV-0018 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Clutch master and slave cylinder refresh kit |  | Walton Toyota |  |  | post_tub_off_inspection | quote_at_walton_toyota | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Condition-based item: inspect first, then buy only if required. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Condition-dependent item; inspect first then buy local only if required. ¦ Quote/pending at Walton Toyota. | Q |  |  |  |  | Parts | 20 | INV-0019 | P4 - Post inspection | 4 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Condenser fan if required |  |  |  |  | post_baseline_only | inspect_then_local_decide | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Legacy planned HVAC item retained as condition-based. | [5 empty] | Parts | 65 | INV-0064 | P4 - Post inspection | 4 | decision_or_timing | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Distributor cap rotor and ignition tune-up consumables |  | Not applicable for current diesel engine |  |  | post_tub_off_inspection | not_required_diesel_engine | replacement_part | inspect_then_decide | cancelled | cancelled | Cancelled: ignition distributor-cap/rotor tune-up consumables are not applicable to the current diesel engine configuration. | cancelled |  |  |  |  | Parts | 21 | INV-0020 | P4 - Post inspection | 4 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Engine mount set |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Condition-based item: inspect first, then buy only if required. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 22 | INV-0021 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Oil filter (genuine Toyota) | 11127 | Toyota Indus | No |  | post_tub_off_inspection | quote_at_toyota_indus | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Toyota Indus quote at direct.toyota-indus.com: Oil Filter - Land Cruiser (1999-2007), part no. 90915-30002. Quote only; do not rebuy elsewhere. | Q |  |  |  | Toyota Genuine Oil Filter | Parts | 23 | INV-0022 | P4 - Post inspection | 4 | Condition-based after tub-off inspection (user confirmed 2026-04-15) | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Engine oil (diesel service fluid - Toyota Indus Dezon CF4 20W-50 4L) | 6000 | Toyota Indus | No |  | post_tub_off_inspection | quote_at_toyota_indus | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Toyota Indus quote at direct.toyota-indus.com: Dezon (CF4 20W-50)-4L, part no. 08883-8004P-CF4. Quote only; do not rebuy elsewhere. | Q | 6000-6000 | 6000 | medium | Toyota Indus Dezon CF4 20W-50 4L | Parts | 23 | INV-0022 | P4 - Post inspection | 4 | Service fluid; confirm engine code before purchase | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Fuel filter |  | Walton Toyota |  |  | post_tub_off_inspection | quote_at_walton_toyota | replacement_part | inspect_then_decide | planned_or_open | needs_confirmation | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ Quote/pending at Walton Toyota. | Q | 5000-20000 | 18000 | High | Diesel parts supplier | Parts | 24 | INV-0023 | P4 - Post inspection | 4 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Fuel-rated rubber hose and clamp kit |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 25 | INV-0024 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Gearbox top-cover service items (detents, bushes, shift-seat kit) |  | Local transmission parts source; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Condition-based item: inspect first, then buy only if required. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 14 | INV-0013 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
HB BODY - U900 CAVITY WAX SPRAY U900 - 400ML | 3699 | Autohub | No | No | post_rust_repair | quote_at_autohub | consumable_material | inspect_then_decide | planned_or_open | needs_confirmation | Autohub 1L cavity wax choice preferred for capacity/value, but not ordered yet. | Q | 2500-4500 | 3699 |  | Autohub cavity wax page | Substances | 8 | INV-0127 | P4 - Post inspection | 4 | post-rust cavity protection | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
HB BODY 999 SEAM SEALER 300ML CARTR | 7696 | Autohub | No | No | post_rust_repair | ordered_in_flight | replacement_part | inspect_then_decide | ordered_in_flight | ordered_in_flight | User confirmed this seam sealer is already ordered from Autohub; keep it in the rust-protection stack but do not rebuy. | ✓ |  |  |  |  | Substances | 5 | INV-0125 | P4 - Post inspection | 4 | already ordered from Autohub | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Heat plugs (glow plugs) set - diesel engine (NEW only) |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User rule 2026-04-15: heat/glow plugs are NEW ONLY; no used/refurbished plugs accepted. ¦ User confirmed replace all items in this service batch with new parts. |  | 12000-36000 | 22000 | High | Bilal Ganj diesel parts + local Toyota diesel supplier | Parts | 29 | INV-0028 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Heater hose set with clamps |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 26 | INV-0025 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Evapo-Rust 5 Litre Heavy Duty Rust Remover |  | 7mart |  |  | post_tub_off_inspection | quote_at_7mart | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote/pending at 7mart as the direct replacement for the out-of-stock Zingfix rust remover. | Q |  |  | high | 7mart Evapo-Rust 5 Litre Heavy Duty Rust Remover | Parts | 32 | INV-0031 | P4 - Post inspection | 4 | Condition-based after tub-off inspection (user confirmed 2026-04-15) | BUY_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
New Battery | 16000 |  | Y | Y | post_tub_off_inspection | inspect_then_local_decide | service_or_replacement_item | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | HaveToCheck ¦ Open item with no procurement evidence yet. ¦ Migrated from Service row 3 into Parts inventory. ¦ User confirmed the new battery is already on hand. | ✓ |  |  |  |  | Service | 3 | INV-0138 | P4 - Post inspection | 4 | decision_or_timing | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Primer | Happilac | Happilac | Q |  | post_tub_off_inspection | quote_at_happilac | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote pending at Happilac for High Build Zinc Phosphate Epoxy Primer; 4L is the practical build size. | Q | 1225-4620 | 3223 | Low | Happilac High Build Zinc Phosphate Epoxy Primer | Parts | 34 | INV-0033 | 4 | 4 | Condition-based after tub-off inspection (user confirmed 2026-04-15) | BUY_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Radiator cap |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 27 | INV-0026 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Radiator hose set upper plus lower with clamps |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 28 | INV-0027 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Remove old LEDS | 5000 | Task only |  |  | post_tub_off_inspection | task_only_not_procurement | service_or_replacement_item | inspect_then_decide | cancelled | cancelled | Cancelled from procurement: removing old LEDs is a work task, not a parts purchase. | cancelled |  |  |  |  | Service | 2 | INV-0137 | P4 - Post inspection | 4 | decision_or_timing | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Steering bushings |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Legacy planned steering service item retained for visibility. ¦ User confirmed replace all items in this service batch with new parts. |  | 3000-12000 | 10000 | High | Local suspension / bush supplier | Parts | 53 | INV-0052 | P4 - Post inspection | 4 | decision_or_timing | BUY_NEW | high | photo_group=chassis_underside; group_photo_count=32; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Suspension Geometry Safety Pack (caster shims + brake hose length check) |  | Pakwheels: https://www.pakwheels.com/accessories-spare-parts/search/-/q_caster+shim+leaf+spring/ ¦ Pakwheels: https://www.pakwheels.com/accessories-spare-parts/search/-/q_brake+hose+toyota+land+cruiser/ ¦ Pakwheels: https://www.pakwheels.com/accessories-spare-parts/search/-/q_steering+damper+toyota+land+cruiser/ |  |  | post_tub_off_inspection | buy_only_if_geometry_or_droop_checks_require | replacement_part | inspect_then_decide | planned_or_open | conditional_pack | Conditional consolidated pack after suspension install checks (caster, hose droop, steering kickback). ¦ Steering damper is already covered by the Ironman kit; keep this pack geometry-only. | planned_or_open | 21000-80000 | 50500 | Medium | https://www.pakwheels.com/accessories-spare-parts/search/-/q_caster+shim+leaf+spring/ ; https://www.pakwheels.com/accessories-spare-parts/search/-/q_brake+hose+toyota+land+cruiser/ ; https://www.pakwheels.com/accessories-spare-parts/search/-/q_steering+damper+toyota+land+cruiser/ | Parts | 257 | INV-0255 | P4 - Post inspection | 4 | inspection_gate | INSPECT_THEN_DECIDE | high | local_serviceable_path | high | low | local_pk_or_on_hand
Thermostat plus gasket | 5000 | PakWheels | No | PKR 5,179 (paid incl shipping) | in_flight_now | track_in_flight_order | replacement_part | inspect_then_decide | ordered_in_flight | needs_confirmation | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ PakWheels order placed: Toyota Prado 1995-2002 Thermostat Valve 90916-03118 Genuine. ¦ Item price PKR 5,000 + shipping PKR 179. | ordered/in-flight | 2000-8000 | 8000 | High | Engine parts supplier | Parts | 30 | INV-0029 | P4 - Post inspection | 4 | procurement_pass2 | INSPECT_THEN_DECIDE | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
Vacuum hose refresh kit |  | Local Toyota/common parts markets; replace new |  |  | post_tub_off_inspection | buy_new_local_batch | replacement_part | inspect_then_decide | planned_or_open | planned_or_open | Active required purchase item from Procurement_Pass2. ¦ RR action=Use local Toyota/common parts markets; buy as one batch after inspection.; evidence=Common Toyota service items should be bought as a local bundle after tub-off inspection confirms exact spec. ¦ User confirmed replace all items in this service batch with new parts. | [5 empty] | Parts | 31 | INV-0030 | P4 - Post inspection | 4 | procurement_pass2 | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
10 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Red ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 78 into Parts inventory. | [5 empty] | Wiring | 78 | INV-0108 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
10 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Black ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 79 into Parts inventory. | [5 empty] | Wiring | 79 | INV-0109 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
10.8 x 4 | 113 | industryparts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 87 into Parts inventory. | [5 empty] | Wiring | 87 | INV-0113 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
100A Circuit Breaker Resettable Fuse Car Marine Boat Automotive Protector | 2000 | Mughal | Y | N |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Jazzcash ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 23 into Parts inventory. | [5 empty] | Wiring | 23 | INV-0077 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
10mm Nylon Braided sleeve Price in Pakistan × 5 | 875 |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 14 into Parts inventory. | [5 empty] | Wiring | 14 | INV-0076 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
10mm Nylon Braided sleeve Price in Pakistan × 5 | 875 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 7 into Parts inventory. | [5 empty] | Wiring | 7 | INV-0070 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
10mm Nylon Braided Sleeve x 5 | 875 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 5 into Parts inventory. | [5 empty] | Wiring | 5 | INV-0068 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
14mm Nylon Braided Sleeve price in Pakistan × 5 | 1500 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 12 into Parts inventory. | [5 empty] | Wiring | 12 | INV-0074 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
14mm Nylon Braided Sleeve price in Pakistan × 5 | 1500 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 8 into Parts inventory. | [5 empty] | Wiring | 8 | INV-0071 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
16 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Red ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 80 into Parts inventory. | [5 empty] | Wiring | 80 | INV-0110 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
16.1 x 4 | 160 | industryparts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 88 into Parts inventory. | [5 empty] | Wiring | 88 | INV-0114 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
16mm Nylon Braided Sleeve x 5 | 1450 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 6 into Parts inventory. | [5 empty] | Wiring | 6 | INV-0069 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
1m, 4 AWG, Red | 11529 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 67 into Parts inventory. | [5 empty] | Wiring | 67 | INV-0101 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
1x 100A LITTEL FUSE ANL Car Fuse MEGA Bolt-on | 1026 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Main Fuse ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 32 into Parts inventory. | [5 empty] | Wiring | 32 | INV-0080 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
20mmn Nylon Braided Sleeve Price in Paklistan × 5 | 1750 |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 13 into Parts inventory. | [5 empty] | Wiring | 13 | INV-0075 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
20mmn Nylon Braided Sleeve Price in Paklistan × 5 | 1750 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 9 into Parts inventory. | [5 empty] | Wiring | 9 | INV-0072 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
25 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Red ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 81 into Parts inventory. | [5 empty] | Wiring | 81 | INV-0111 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
25.1 x 4 | 160 | industryparts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 89 into Parts inventory. | [5 empty] | Wiring | 89 | INV-0115 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
35.1 x 4 | 225 | industryparts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 90 into Parts inventory. | [5 empty] | Wiring | 90 | INV-0116 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
35mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Black 1.5m ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 82 into Parts inventory. | [5 empty] | Wiring | 82 | INV-0112 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
4 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Green ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 75 into Parts inventory. | [5 empty] | Wiring | 75 | INV-0105 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
5 Pin 40A Car Relay 12V x 6 | 8196 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Relays ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 41 into Parts inventory. | [5 empty] | Wiring | 41 | INV-0086 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
555 Black Red Terminal M8 Blocks Power Supply Terminals Welding Machine Inverter Post Connector x 10 | 3275 | Digilog | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 97 into Parts inventory. | [5 empty] | Wiring | 97 | INV-0119 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
6 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Red ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 76 into Parts inventory. | [5 empty] | Wiring | 76 | INV-0106 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
6 Way Distribution Block Car Midi Fuse Box Block Holder 200A Bolt | 18101 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 27 into Parts inventory. | [5 empty] | Wiring | 27 | INV-0078 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
6pcs Ratchet Crimping Tool Set | 11964 | Temu | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 54 into Parts inventory. | [5 empty] | Wiring | 54 | INV-0096 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
70.12 x 10 | 1313 | industryparts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 91 into Parts inventory. | [5 empty] | Wiring | 91 | INV-0117 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
8 mm² |  |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Red ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 77 into Parts inventory. | [5 empty] | Wiring | 77 | INV-0107 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
8mm Nylon Braided Sleeve x 5 | 800 | electronicsstore.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 4 into Parts inventory. | [5 empty] | Wiring | 4 | INV-0067 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Bare Copper Braid Tape | 12500 | industryparts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 92 into Parts inventory. | [5 empty] | Wiring | 92 | INV-0118 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
body_floor | existing |  | Y |  | body_structure | repair_in_place | existing_component | restore_and_reuse | in_progress_weld_repair | reuse_existing | RR action=close_floor_rust_map_and_repair_scope; evidence=akber_khan-00798 ¦ Tub/chassis weld repair planned before final paint; keep as repair/reuse path. | ✓ |  |  |  |  | Restore_Replace | 11 | INV-0148 | In progress - bodywork | 1 | manual_bodywork_update_2026_04_15 | REFRESH_EXISTING | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
body_sections | existing |  | Y |  | body_and_weather_seal | refurbish_send_out | existing_component | restore_and_reuse | in_progress_refresh | reuse_existing | RR action=confirm_vendor_scope_and_return_condition; evidence=akber_khan-00796 ¦ Lower body section repair/refinish in progress; no new panel buy unless weld inspection finds non-repairable areas. | ✓ |  |  |  |  | Restore_Replace | 6 | INV-0143 | In progress - bodywork | 1 | manual_bodywork_update_2026_04_15 | REFRESH_EXISTING | medium | photo_group=body_exterior; group_photo_count=6; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Classification of Deutsch DT Series Connectors, Size 16 Stamped Contacts, Automotive Electrical Connectors, 188pcs x 2 | 17644 | Temu | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 53 into Parts inventory. | [5 empty] | Wiring | 53 | INV-0095 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
Contact Cleaner 400ML × 1 | 1800 | ToolsMart.pk | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 22 into Parts inventory. | [5 empty] | Substances | 22 | INV-0136 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Copper Cable Lug 16mm cable 8mm Bolt Hole Pakistan × 10 | 280 | fiaz.com.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 45 into Parts inventory. | [5 empty] | Wiring | 45 | INV-0087 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Dielectric Grease | 5609 | AliExpress |  | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 2 into Parts inventory. | [5 empty] | Substances | 2 | INV-0122 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
Dielectric Grease | 11529 | adenwalla.net |  |  | post_baseline_only | no_additional_buy_duplicate_entry | consumable_material | inspect_then_decide | procured_or_on_hand | procured_or_on_hand | Duplicate? Needed? ¦ Open item with no procurement evidence yet. ¦ Migrated from Substances row 3 into Parts inventory. ¦ Reconciled 2026-04-15: duplicate of procured Dielectric Grease line; no additional purchase required. | [5 empty] | Substances | 3 | INV-0123 | Done / On hand | 0 | Duplicate resolved against procured Dielectric Grease line | INSPECT_THEN_DECIDE | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
doors | existing |  | Y |  | body_and_weather_seal | refurbish_send_out | existing_component | restore_and_reuse | completed_refresh | reuse_existing | RR action=confirm_vendor_scope_and_return_condition; evidence=fj40-00229¦akber_khan-00568¦akber_khan-00705¦akber_khan-00796 ¦ Doors repainted; reuse existing unless hidden damage appears at final fit-up. | ✓ |  |  |  |  | Restore_Replace | 3 | INV-0140 | Done / On hand | 0 | manual_bodywork_update_2026_04_15 | REFRESH_EXISTING | medium | photo_group=removable_panels; group_photo_count=13; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
electrical_accessories | existing |  | Y |  | electrical | remove_nonbaseline_and_refit_clean | existing_component | restore_and_reuse | existing_reuse | reuse_existing | RR action=finish_deletion_of_old_accessory_wiring; evidence=fj40-00251 | ✓ |  |  |  |  | Restore_Replace | 10 | INV-0147 | Done / On hand | 0 | status | REFRESH_EXISTING | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Engine-specific compressor bracket and belt solution | re-use | [5 empty] | existing_component | restore_and_reuse | existing_reuse | reuse_existing | Marked for re-use, not replacement purchase. | ✓ | 15000-50000 | 40000 | High | Fabricator | Parts | 9 | INV-0008 | Done / On hand | 0 | status | REFRESH_EXISTING | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Grommet Set | 18600 | starshop.pk |  | 9200 COD | post_baseline_only | defer_as_non_baseline | replacement_part | deferred_decision | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 3 into Parts inventory. ¦ RR action=No supplier action now.; evidence=Entry is already explicitly deferred or duplicate against selected baseline. | [5 empty] | Wiring | 3 | INV-0066 | Done / On hand | 0 | procurement_pass2 | DEFER_DECISION | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | medium | low | local_pk_or_on_hand
H4 Ceramic Headlight Connector | 1350 | Auto Xpert | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 51 into Parts inventory. | [5 empty] | Wiring | 51 | INV-0093 | Done / On hand | 0 | procurement_pass2 | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
heat shrink tubing (various sizes) x 2 | 4200 | IndustryParts.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 10 into Parts inventory. | [5 empty] | Wiring | 10 | INV-0073 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
hood | existing |  | Y |  | body_and_weather_seal | refurbish_send_out | existing_component | restore_and_reuse | planned_refresh | reuse_existing | RR action=confirm_vendor_scope_and_return_condition; evidence=akber_khan-00796 ¦ Retain refresh path; buy only if post-weld/post-paint inspection finds non-repairable damage. | ✓ | 1000-5000 | 5000 | Low | Local rubber supplier | Restore_Replace | 5 | INV-0142 | P5 - Later phase | 5 | manual_bodywork_update_2026_04_15 | REFRESH_EXISTING | medium | photo_group=body_exterior; group_photo_count=6; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
https://uni-core.pk/product/cables-wires/flexible-cables/2-5mmsq-flexible-cable/ - blue | 9080 | uni-core.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 72 into Parts inventory. | [5 empty] | Wiring | 72 | INV-0102 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
https://uni-core.pk/product/flexible-cables/1-5mmsq-flexible-cable/ - yellow | 5770 | uni-core.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 73 into Parts inventory. | [5 empty] | Wiring | 73 | INV-0103 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
https://uni-core.pk/product/flexible-cables/1mmsq-flexible-cable/ - white | 4430 | uni-core.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 74 into Parts inventory. | [5 empty] | Wiring | 74 | INV-0104 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Insulated Thimbles female lug 2.5mm Blue in Pakistan × 1 | 450 | fiaz.com.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 49 into Parts inventory. | [5 empty] | Wiring | 49 | INV-0091 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Insulated Thimbles Male lug 2.5mm Blue in Pakistan × 1 | 700 | fiaz.com.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 48 into Parts inventory. | [5 empty] | Wiring | 48 | INV-0090 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
interior | existing |  | Y |  | interior_refit | clean_store_for_reuse | existing_component | restore_and_reuse | existing_reuse | reuse_existing | RR action=complete_tagging_and_damage_check; evidence=akber_khan-00793¦akber_khan-00796¦akber_khan-00808 | ✓ |  |  |  |  | Restore_Replace | 9 | INV-0146 | Done / On hand | 0 | status | REFRESH_EXISTING | high | photo_group=interior_cabin; group_photo_count=24; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Lithium Grease + PTFE 400ML × 1 | 2200 | ToolsMart.pk | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 21 into Parts inventory. | [5 empty] | Substances | 21 | INV-0135 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Littelfuse Bolt-down Automotive Fuse MIDI/498 Auto Fuse 30A x2 | 3409 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 34 into Parts inventory. | [5 empty] | Wiring | 34 | INV-0082 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
Littelfuse Bolt-down Automotive Fuse MIDI/498 Auto Fuse 50A |  | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 35 into Parts inventory. | [5 empty] | Wiring | 35 | INV-0083 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
Littelfuse Bolt-down Automotive Fuse MIDI/498 Auto Fuse 50A |  | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 36 into Parts inventory. | [5 empty] | Wiring | 36 | INV-0084 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
Littelfuse Bolt-down Automotive Fuse MIDI/498 Auto Fuse 60A | 843 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 37 into Parts inventory. | [5 empty] | Wiring | 37 | INV-0085 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
Loctite 290 – Medium/High Strength Wicking Grade Threadlocker × 1 | 1520 | ToolsMart.pk | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 20 into Parts inventory. |  | 3000-10000 | 8000 | Medium | Hardware / tool supplier | Substances | 20 | INV-0134 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
MOMO Carbon Fiber Steering Wheel | 8444 | pakwheels | Y | Y |  |  | replacement_part | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. | ✓ |  |  |  |  | Parts | 6 | INV-0005 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=chassis_underside; group_photo_count=32; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
O-type Blue Insulated Thimble/ Cable Lug 2.5mm × 1 | 250 | fiaz.com.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 47 into Parts inventory. | [5 empty] | Wiring | 47 | INV-0089 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
O-type Yellow Insulated Thimble/ Cable Lug 4mm (6mm hole) × 1 | 750 | fiaz.com.pk | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 50 into Parts inventory. | [5 empty] | Wiring | 50 | INV-0092 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
PERMATEX 81150 DIE ELECTRIC TUNE UP GREASE 0.33 OZ | 1288 | Adenwalla & Sons |  | COD |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 4 into Parts inventory. | [5 empty] | Substances | 4 | INV-0124 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Permatex Copper Anti Seize Lubricant Premium Quality in Pakistan | 11000 | Pakistan Power Tool | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 14 into Parts inventory. | [5 empty] | Substances | 14 | INV-0129 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Portable 12-Way Car Fuse Box Universal Automotive Box Holder with Led Indicator | 4000 | Mughal | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 33 into Parts inventory. | [5 empty] | Wiring | 33 | INV-0081 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
RAPTOR LINER TINTABLE STANDARD 3.8L KIT | 39900 | adenwalla | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 15 into Parts inventory. | [5 empty] | Substances | 15 | INV-0130 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Relay Box 12V 10 Way Relay Block and 10 Way ATC/ATO Blade Fuse Pane | 37924 | AliExpress | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 28 into Parts inventory. | [5 empty] | Wiring | 28 | INV-0079 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | high | import_cn_or_global
roof | existing |  | Y |  | body_and_weather_seal | refurbish_send_out | existing_component | restore_and_reuse | planned_refresh | reuse_existing | RR action=confirm_vendor_scope_and_return_condition; evidence=fj40-00133¦fj40-00229¦akber_khan-00796 ¦ Retain roof refresh path with channel repair; replace only if repair scope fails. | ✓ |  |  |  |  | Restore_Replace | 2 | INV-0139 | P5 - Later phase | 5 | manual_bodywork_update_2026_04_15 | REFRESH_EXISTING | low | photo_group=roof_and_gutters; group_photo_count=4; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
ROST FLASH PRO | 1365 | adenwalla | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Freeing bolts ¦ Evidence indicates purchased/received. ¦ Migrated from Substances row 13 into Parts inventory. | [5 empty] | Substances | 13 | INV-0128 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
rubbers_and_seals | existing |  | Y |  | body_and_weather_seal | refurbish_service_subcomponents | existing_component | restore_and_reuse | existing_reuse | reuse_existing | RR action=service_mechanisms_and_rubbers_before_refit; evidence=akber_khan-00796¦akber_khan-00797 | ✓ |  |  |  |  | Restore_Replace | 8 | INV-0145 | Done / On hand | 0 | status | REFRESH_EXISTING | low | photo_group=rubbers_and_seals; group_photo_count=1; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Sanden-type compressor | re-use | [5 empty] | existing_component | restore_and_reuse | existing_reuse | reuse_existing | Marked for re-use, not replacement purchase. | ✓ |  |  |  |  | Parts | 8 | INV-0007 | Done / On hand | 0 | status | REFRESH_EXISTING | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Steelmate Central Locking System | 4680 | Autostore.pk | Y | Y |  |  | replacement_part | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. | ✓ |  |  |  |  | Parts | 7 | INV-0006 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Toyota Land Cruiser FJ40 Neoprene Top Cover - Model 1960-1984 | 11500 | Autozcare | Y | Y |  |  | replacement_part | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. | ✓ |  |  |  |  | Parts | 2 | INV-0001 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Universal 4-inch Switch Panel 3pcs | 4290 | chaudhryautostore | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Rocker Switches ¦ Evidence indicates purchased/received. ¦ Migrated from Wiring row 57 into Parts inventory. | [5 empty] | Wiring | 57 | INV-0097 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
VMD Brake and Clutch Cleaner 400ML × 1 | 1840 | ToolsMart.pk | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 19 into Parts inventory. | [5 empty] | Substances | 19 | INV-0133 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=engine_bay; group_photo_count=10; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
VMD Unlocking Protective Lubricating Agent 200ML × 1 | 1060 | ToolsMart.pk | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 18 into Parts inventory. | [5 empty] | Substances | 18 | INV-0132 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
WD-40 Multi-Use Product Handy Can 200ml (Pack Of 3) | 2300 | adenwalla | Y | Y |  |  | consumable_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Substances row 16 into Parts inventory. | [5 empty] | Substances | 16 | INV-0131 | Done / On hand | 0 | status | BUY_NEW | medium | photo_group=body_floor; group_photo_count=15; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
window_hardware | existing |  | Y |  | body_and_weather_seal | refurbish_service_subcomponents | existing_component | restore_and_reuse | existing_reuse | reuse_existing | RR action=service_mechanisms_and_rubbers_before_refit; evidence=akber_khan-00796 | ✓ |  |  |  |  | Restore_Replace | 7 | INV-0144 | Done / On hand | 0 | status | REFRESH_EXISTING | low | photo_group=window_hardware; group_photo_count=1; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
windows | existing |  | Y |  | body_and_weather_seal | refurbish_send_out | existing_component | restore_and_reuse | planned_refresh | reuse_existing | RR action=confirm_vendor_scope_and_return_condition; evidence=akber_khan-00568¦akber_khan-00796 ¦ Glass/frame retained; inspect seals at final fit-up before buying replacements. | ✓ |  |  |  |  | Restore_Replace | 4 | INV-0141 | P5 - Later phase | 5 | manual_bodywork_update_2026_04_15 | REFRESH_EXISTING | low | photo_group=window_hardware; group_photo_count=1; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Wire Insulation Heat Shrink Tubes | 3999 |  | Y | Y |  |  | wiring_material | replace_or_procure | procured_or_on_hand | procured_or_on_hand | Evidence indicates purchased/received. ¦ Migrated from Wiring row 102 into Parts inventory. | [5 empty] | Wiring | 102 | INV-0120 | Done / On hand | 0 | status | BUY_NEW | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Maximus Under Seat Subwoofer Box With Built in Amplifier - Compact Active Bass Woofer for Cars | 25100 | SehgalMotors.PK |  | Cancelled? | revovate existing |  | replacement_part | cancelled | cancelled | cancelled | Marked cancelled. | cancelled |  |  |  |  | Parts | 3 | INV-0002 | Cancelled | 99 | status | CANCELLED | medium | photo_group=documentation_reference; group_photo_count=5; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Universal Android LCD Tab 9 Inches With Wiring - Without Main Grip × 1 | 14600 | ]ehgalMotors.PK |  | Cancelled? |  |  | replacement_part | cancelled | cancelled | cancelled | Marked cancelled. | cancelled |  |  |  |  | Parts | 4 | INV-0003 | Cancelled | 99 | status | CANCELLED | high | photo_group=electrical_system; group_photo_count=52; spot_checked=20260410_013927,20260411_065030,20260324_004852,20260323_210944,20260408_211754,20260413_005435,20260405_234652,20260321_235600,20260317_235150 | high | low | local_pk_or_on_hand
Hidden evaporator/heater/defrost unit, compact Mini-size (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | quote_at_bilal_ganj_vitz_cabin_hvac | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote pending via Bilal Ganj. Take from one early-2000s manual-AC Toyota Vitz donor, cabin-side only. Include evaporator core, heater core, blower motor, TXV, blower resistor, ducts, and intact pigtails if attached. Do not include the 3-knob control panel; that is already on hand. | Q |  |  | High | Bilal Ganj quote pending | Parts | 16 | INV-0257 | P3 - Audit then buy | 3 | P3 cabin HVAC donor quote (manual-AC Vitz, cabin side only) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; donor_selection=bilal_ganj_vitz_manual_ac | high | medium | local_pk_or_on_hand
Slim under-dash louver outlet panel (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | quote_at_bilal_ganj_vitz_cabin_hvac | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote pending via Bilal Ganj. Take from the same early-2000s manual-AC Toyota Vitz donor, cabin-side only. | Q |  |  | High | Bilal Ganj quote pending | Parts | 17 | INV-0258 | P3 - Audit then buy | 3 | P3 cabin HVAC donor quote (manual-AC Vitz, cabin side only) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; donor_selection=bilal_ganj_vitz_manual_ac | high | medium | local_pk_or_on_hand
Separate 3-knob control panel (Vitz donor) |  | On hand | Y | Y | pre_dash_refit | use_existing_3_knob_control | replacement_part | replace_or_procure | procured_or_on_hand | procured_or_on_hand | User confirmed the 3-knob control is already on hand; no purchase needed for this control panel. | ✓ |  |  | High | Bilal Ganj quote pending | Parts | 18 | INV-0259 | P3 - Audit then buy | 3 | covered by on-hand 3-knob control panel | INSPECT_THEN_DECIDE | medium | photo_group=documentation_reference; donor_selection=bilal_ganj_vitz_manual_ac | high | low | local_pk_or_on_hand
2.5-inch duct hose and defrost hose kit (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | quote_at_bilal_ganj_vitz_cabin_hvac | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote pending via Bilal Ganj. Take from the same early-2000s manual-AC Toyota Vitz donor, cabin-side only. | Q |  |  | High | Bilal Ganj quote pending | Parts | 19 | INV-0260 | P3 - Audit then buy | 3 | P3 cabin HVAC donor quote (manual-AC Vitz, cabin side only) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; donor_selection=bilal_ganj_vitz_manual_ac | high | medium | local_pk_or_on_hand
Drain hose and mounting kit (Vitz donor) |  | Bilal Ganj | No |  | pre_dash_refit | quote_at_bilal_ganj_vitz_cabin_hvac | replacement_part | replace_or_procure | planned_or_open | needs_confirmation | Quote pending via Bilal Ganj. Take from the same early-2000s manual-AC Toyota Vitz donor, cabin-side only. | Q |  |  | High | Bilal Ganj quote pending | Parts | 20 | INV-0261 | P3 - Audit then buy | 3 | P3 cabin HVAC donor quote (manual-AC Vitz, cabin side only) | SERVICE_OR_NEW | medium | photo_group=documentation_reference; donor_selection=bilal_ganj_vitz_manual_ac | high | medium | local_pk_or_on_hand