## ACTIVE_PARTS
item | quantity | likely source if from another car | needs mechanic checked | expected price | image to show | purchase stage | what to verify | all image refs | source row | existing one ok? (analysis) | buy_decision_now | cleanup_reason | cleanup_action | pakistan_quality_recommendation | verified_source_url | decision_today | primary_purchase_link | backup_purchase_link | procurement_status | purchased_qty | purchased_on | purchased_est_cost_pkr | purchase_notes | price_min_pkr | price_max_pkr | price_mid_pkr | parts_tab_procured | parts_tab_status_hint | include_in_remaining_budget | dedup_key | duplicate_count
Kit A bolt - M10x1.25 class 8.8 hex bolt | 16 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1400-2800 | images/20260405_234546.jpg | BUY_NOW | Head mark 8.8, pitch-gauge check, length by sample | 20260405_234546.jpg;20260405_234802.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | ON_HAND_USE_AFTER_LENGTH_PITCH_CHECK | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | VERIFY_BEFORE_USE |  |  | TRUSTED_ON_HAND | ~50 bolts purchased (market) | 2026-04-16 | Not logged | User confirmed trusted market bolts. Still confirm exact length/pitch per mount location before final torque. | 1400 | 2800 | 2100 | no | planned_or_open | NO | kit a bolt - m10x1.25 class 8.8 hex bolt | 1
Kit A nut - M10 nyloc/all-metal mix | 24 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1200-2400 | images/20260405_234546.jpg | BUY_NOW | Thread fit and lock quality | 20260405_234546.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1200 | 2400 | 1800 | no | planned_or_open | YES | kit a nut - m10 nyloc/all-metal mix | 1
Kit A washer - M10 flat washer | 40 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 400-900 | images/20260405_234546.jpg | BUY_NOW | ID/OD match cups and bolt | 20260405_234546.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 400 | 900 | 650 | no | planned_or_open | YES | kit a washer - m10 flat washer | 1
Kit A spring washer - M10 spring washer | 20 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 300-650 | images/20260405_234546.jpg | BUY_NOW | No cracks, consistent spring | 20260405_234546.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 300 | 650 | 475 | no | planned_or_open | YES | kit a spring washer - m10 spring washer | 1
Kit A sleeve/spacer - Sleeve for M10 mount points | 16 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1200-3200 | images/20260405_234652.jpg | BUY_NOW | ID/OD/length match stack | 20260405_234652.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1200 | 3200 | 2200 | no | planned_or_open | YES | kit a sleeve/spacer - sleeve for m10 mount points | 1
Kit A bolt - M12 class 8.8 hex bolt | 4 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 600-1400 | images/20260405_234802.jpg | BUY_NOW | Head mark 8.8, length by sample | 20260405_234802.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | ON_HAND_USE_AFTER_LENGTH_PITCH_CHECK | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | VERIFY_BEFORE_USE |  |  | TRUSTED_ON_HAND | ~50 bolts purchased (market) | 2026-04-16 | Not logged | User confirmed trusted market bolts. Still confirm exact length/pitch per mount location before final torque. | 600 | 1400 | 1000 | no | planned_or_open | NO | kit a bolt - m12 class 8.8 hex bolt | 1
Kit A nut - M12 nut | 6 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 500-1100 | images/20260405_234802.jpg | BUY_NOW | Thread clean, pitch match | 20260405_234802.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 500 | 1100 | 800 | no | planned_or_open | YES | kit a nut - m12 nut | 1
Kit A washer - M12 flat washer | 12 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 200-500 | images/20260405_234802.jpg | BUY_NOW | ID/OD match | 20260405_234802.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 200 | 500 | 350 | no | planned_or_open | YES | kit a washer - m12 flat washer | 1
Kit A spring washer - M12 spring washer | 6 (+20% spare) | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 150-350 | images/20260405_234802.jpg | BUY_NOW | Consistent tension | 20260405_234802.jpg | 244 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 150 | 350 | 250 | no | planned_or_open | YES | kit a spring washer - m12 spring washer | 1
Kit B bolt - M6x1.0 class 8.8 hex bolts lengths 12/16/20/25mm | 220 total | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 6000-13000 | images/20260405_234546.jpg | BUY_NOW | Confirm mix by length | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 6000 | 13000 | 9500 | no | planned_or_open | YES | kit b bolt - m6x1.0 class 8.8 hex bolts lengths 12/16/20/25mm | 1
Kit B nuts - M6 nyloc | 160 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 3200-6400 | images/20260405_234546.jpg | BUY_NOW | Nylon insert quality | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 3200 | 6400 | 4800 | no | planned_or_open | YES | kit b nuts - m6 nyloc | 1
Kit B nuts - M6 flange nuts | 80 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1200-2800 | images/20260405_234546.jpg | BUY_NOW | Flange face true | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1200 | 2800 | 2000 | no | planned_or_open | YES | kit b nuts - m6 flange nuts | 1
Kit B washers - M6 flat washers | 300 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 900-2400 | images/20260405_234546.jpg | BUY_NOW | Consistent thickness | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 900 | 2400 | 1650 | no | planned_or_open | YES | kit b washers - m6 flat washers | 1
Kit B spring washers - M6 spring washers | 140 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 600-1700 | images/20260405_234546.jpg | BUY_NOW | No cracks | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 600 | 1700 | 1150 | no | planned_or_open | YES | kit b spring washers - m6 spring washers | 1
Kit B bolt - M8x1.25 class 8.8 bolts lengths 16/20/25/30mm | 120 total | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 4800-10800 | images/20260405_234546.jpg | BUY_NOW | Confirm mix by length | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 4800 | 10800 | 7800 | no | planned_or_open | YES | kit b bolt - m8x1.25 class 8.8 bolts lengths 16/20/25/30mm | 1
Kit B nuts - M8 nyloc | 90 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 2700-6300 | images/20260405_234546.jpg | BUY_NOW | Nylon insert quality | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 2700 | 6300 | 4500 | no | planned_or_open | YES | kit b nuts - m8 nyloc | 1
Kit B nuts - M8 flange nuts | 40 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1000-2200 | images/20260405_234546.jpg | BUY_NOW | Flange face true | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1000 | 2200 | 1600 | no | planned_or_open | YES | kit b nuts - m8 flange nuts | 1
Kit B washers - M8 flat washers | 180 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 900-2500 | images/20260405_234546.jpg | BUY_NOW | Consistent thickness | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 900 | 2500 | 1700 | no | planned_or_open | YES | kit b washers - m8 flat washers | 1
Kit B spring washers - M8 spring washers | 90 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 600-1600 | images/20260405_234546.jpg | BUY_NOW | No cracks | 20260405_234546.jpg | 245 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 600 | 1600 | 1100 | no | planned_or_open | YES | kit b spring washers - m8 spring washers | 1
Kit C captive nut - M6 captive/clip nuts | 120 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1800-4200 | images/20260405_234546.jpg | BUY_NOW | Plating + thread quality | 20260405_234546.jpg | 246 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1800 | 4200 | 3000 | no | planned_or_open | YES | kit c captive nut - m6 captive/clip nuts | 1
Kit C captive nut - M8 captive/clip nuts | 60 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1500-3300 | images/20260405_234546.jpg | BUY_NOW | Plating + thread quality | 20260405_234546.jpg | 246 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1500 | 3300 | 2400 | no | planned_or_open | YES | kit c captive nut - m8 captive/clip nuts | 1
Kit C weld nut - M6 weld nuts | 30 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 600-1500 | images/20260405_234546.jpg | BUY_NOW | Thread quality | 20260405_234546.jpg | 246 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 600 | 1500 | 1050 | no | planned_or_open | YES | kit c weld nut - m6 weld nuts | 1
Kit C weld nut - M8 weld nuts | 20 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 700-1600 | images/20260405_234546.jpg | BUY_NOW | Thread quality | 20260405_234546.jpg | 246 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 700 | 1600 | 1150 | no | planned_or_open | YES | kit c weld nut - m8 weld nuts | 1
Kit C rivnut - M6 steel rivnuts | 30 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 900-2100 | images/20260405_234546.jpg | BUY_NOW | Wall/knurl quality | 20260405_234546.jpg | 246 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 900 | 2100 | 1500 | no | planned_or_open | YES | kit c rivnut - m6 steel rivnuts | 1
Kit C rivnut - M8 steel rivnuts | 20 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 900-2200 | images/20260405_234546.jpg | BUY_NOW | Wall/knurl quality | 20260405_234546.jpg | 246 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 900 | 2200 | 1550 | no | planned_or_open | YES | kit c rivnut - m8 steel rivnuts | 1
Kit D star washer - M6 star/serrated washer | 120 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 700-1800 | images/20260411_065030.jpg | BUY_NOW | Sharp serrations | 20260411_065030.jpg | 247 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 700 | 1800 | 1250 | no | planned_or_open | YES | kit d star washer - m6 star/serrated washer | 1
Kit D star washer - M8 star/serrated washer | 80 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 800-2200 | images/20260411_065030.jpg | BUY_NOW | Sharp serrations | 20260411_065030.jpg | 247 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 800 | 2200 | 1500 | no | planned_or_open | YES | kit d star washer - m8 star/serrated washer | 1
Kit D star washer - M10 star/serrated washer | 40 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 700-1700 | images/20260411_065030.jpg | BUY_NOW | Sharp serrations | 20260411_065030.jpg | 247 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 700 | 1700 | 1200 | no | planned_or_open | YES | kit d star washer - m10 star/serrated washer | 1
Kit D flange nut - M6 serrated flange nut | 40 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 800-1800 | images/20260411_065030.jpg | BUY_NOW | Serrations intact | 20260411_065030.jpg | 247 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 800 | 1800 | 1300 | no | planned_or_open | YES | kit d flange nut - m6 serrated flange nut | 1
Kit D flange nut - M8 serrated flange nut | 20 | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 700-1500 | images/20260411_065030.jpg | BUY_NOW | Serrations intact | 20260411_065030.jpg | 247 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 700 | 1500 | 1100 | no | planned_or_open | YES | kit d flange nut - m8 serrated flange nut | 1
Kit D paste - Conductive anti-corrosion paste | 1 tube | New hardware/electrical market (not donor car) | Optional (sample-check) | PKR 1200-3500 | images/20260411_065030.jpg | BUY_NOW | Electrical-ground suitable | 20260411_065030.jpg | 247 | No. Use new hardware only; old mixed bolts/nuts are not reliable for final assembly. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 1200 | 3500 | 2350 | no | planned_or_open | YES | kit d paste - conductive anti-corrosion paste | 1
Body mount rubber - OEM-style body mount insulator set | Full set | New replacement market (not used donor) | Yes | PKR 15000-60000 | images/20260405_234546.jpg | BUY_NOW | Match sleeve ID/OD/length + stack | 20260405_234546.jpg;20260405_234652.jpg | 12 | Maybe. Reuse only if old rubbers are not crushed/cracked and stack height matches; usually replace. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 15000 | 60000 | 37500 | no | planned_or_open | YES | body mount rubber - oem-style body mount insulator set | 1
Shims/spacers - M10/M12 shim pack thickness 1/2/3/5mm | Assorted full pack | New replacement market (not used donor) | Yes | PKR 3000-12000 | images/20260405_234652.jpg | BUY_NOW | Use for tub leveling | 20260405_234652.jpg | 13 | Yes (partly). Existing shims can be reused if flat/rust-free, but buy a fresh assortment for alignment. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 3000 | 12000 | 7500 | no | planned_or_open | YES | shims/spacers - m10/m12 shim pack thickness 1/2/3/5mm | 1
Ignition barrel - Matched key ignition lock set or re-key service | 1 set | Toyota donor lock set + locksmith service OR new lock set | Yes | PKR 4000-25000 | images/20260323_180218.jpg | BUY_NOW | ACC/IGN/START smooth, minimal play | 20260323_180218.jpg;20260323_190047.jpg | 41 | No as-is. Existing lock has poor security; re-key/service or replace. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 4000 | 25000 | 14500 | no | planned_or_open | YES | ignition barrel - matched key ignition lock set or re-key service | 1
Fuse box - Compact covered ATO/ATC fuse block 6-way | 3 identical | Toyota donor fuse boxes or new compact covered aftermarket | Yes | PKR 11100-21000 | images/20260411_065030.jpg | BUY_NOW | Covered body, firm lid, strong terminals | 20260411_065030.jpg;20260411_143135.jpg | 186 | Maybe. Reuse original Toyota-style boxes only if terminals are tight and no heat damage. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | Prefer compact new covered fuse boxes online; keep original-style form factor. | https://wellshop.pk/product/6-way-fuse-block-blade-fuse-box-holder-dc-12-32v-1-709607/ | BUY_NOW | https://wellshop.pk/product/6-way-fuse-block-blade-fuse-box-holder-dc-12-32v-1-709607/ | https://sehgalmotors.pk/products/fuse-60a-box-fuse-kit-for-trucks-and-cars | NOT_PURCHASED |  |  |  |  | 11100 | 21000 | 16050 | no | planned_or_open | YES | fuse box - compact covered ato/atc fuse block 6-way | 1
EPS kit - Complete EPS column kit with ECU, shafts, U-joints, couplers, brackets, connectors | 1 complete kit | Toyota donor EPS column set (Bilal Ganj: Prius/Corolla/Vitz candidates) | Yes | PKR 54000-136000 | images/20260321_235600.jpg | BUY_NOW | Bench-test smooth assist; no lash/noise; pigtails >=150mm | 20260321_235600.jpg;20260406_031010.jpg | 229 | N/A upgrade choice. Existing steering can stay if skipping EPS; EPS is optional improvement. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | Bilal Ganj only. Buy complete and bench-tested EPS set; no incomplete kits. | Bilal Ganj inspection only | BILAL_GANJ_ONLY | Bilal Ganj (in-person complete kit verification) | N/A | NOT_PURCHASED |  |  |  |  | 54000 | 136000 | 95000 | no | planned_or_open | YES | eps kit - complete eps column kit with ecu, shafts, u-joints, couplers, brackets, connectors | 1
Heat plugs / glow plugs - Diesel glow plug set (thread/reach/voltage per engine code) | Full set | New parts market only (no used donor plugs) | Yes | PKR 12000-36000 | images/20260317_235150.jpg | BUY_IF_ENGINE_CODE_MATCH | New only; no used/refurbished plugs | 20260317_235150.jpg | 29 | No. Glow/heat plugs should be new only. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | Buy new only (engine code/thread/reach confirmed first). | https://cruisercorps.com/products/ngk-3b-diesel-glow-plug-set-of-4 | BUY_AFTER_ENGINE_CODE | https://www.pakwheels.com/accessories-spare-parts/search/-/q_glow%20plug/ | https://www.daraz.pk/catalog/?q=toyota+glow+plug | NOT_PURCHASED |  |  |  |  | 12000 | 36000 | 24000 | no | planned_or_open | YES | heat plugs / glow plugs - diesel glow plug set (thread/reach/voltage per engine code) | 1
Local front leaf spring pack (new, custom to measured dimensions) | 2 packs | Pakistan local spring manufacturer (Landhi preferred, Popular backup) | Yes | PKR 35000-90000 | images/20260324_004852.jpg | MEASURE_THEN_BUY_ACTIVE | Buy only after measured fit confirmation | 20260324_004852.jpg;20260411_220207.jpg | 15 | Maybe. Keep existing only if no cracks, no sag, and bush eyes are within tolerance after mechanic inspection. | MEASURE_FIRST_THEN_BUY | Active local front leaf spring path. | KEPT_IN_ACTIVE | Order custom measured leaf pack from LEW first; use Popular as backup if lead time/price better. | https://spring.com.pk/ ; https://popularspringind.com/ | ACTIVE_SUSPENSION_CORE_ORDER_BY_QUOTE | https://spring.com.pk/contact-us/ | https://popularspringind.com/ | NOT_PURCHASED |  |  |  |  | 35000 | 90000 | 62500 | no | planned_or_open | YES | local front leaf spring pack (new, custom to measured dimensions) | 1
Local rear leaf spring pack (new, custom to measured dimensions) | 2 packs | Pakistan local spring manufacturer (Landhi preferred, Popular backup) | Yes | PKR 35000-90000 | images/20260324_004852.jpg | MEASURE_THEN_BUY_ACTIVE | Buy only after measured fit confirmation | 20260324_004852.jpg;20260411_220214.jpg | 16 | Maybe. Keep existing only if no cracks, no inversion risk, and ride height is acceptable after load check. | MEASURE_FIRST_THEN_BUY | Active local rear leaf spring path. | KEPT_IN_ACTIVE | Order custom measured leaf pack from LEW first; use Popular as backup if lead time/price better. | https://spring.com.pk/ ; https://popularspringind.com/ | ACTIVE_SUSPENSION_CORE_ORDER_BY_QUOTE | https://spring.com.pk/contact-us/ | https://popularspringind.com/ | NOT_PURCHASED |  |  |  |  | 35000 | 90000 | 62500 | no | planned_or_open | YES | local rear leaf spring pack (new, custom to measured dimensions) | 1
Steering bushings - Steering linkage bush set | 1 set | New hardware/electrical market (not donor car) | Yes | PKR 3000-12000 | images/20260406_031010.jpg | INSPECT_THEN_BUY_ACTIVE | Condition-based quote | 20260406_031010.jpg | 230 | Maybe. Replace only if measurable play, cracking, or steering looseness persists after service. | BUY_ONLY_IF_PLAY_FOUND | Steering bushing only if wear/play confirmed. | KEPT_IN_ACTIVE | Use only if play exists. Prefer new bushings from verified supplier; avoid random used pieces. | https://www.pakwheels.com/accessories-spare-parts/search/-/ct_steering-suspension/ | CONDITIONAL | https://www.pakwheels.com/accessories-spare-parts/search/-/ct_steering-suspension/ |  | NOT_PURCHASED |  |  |  |  | 3000 | 12000 | 7500 | no | planned_or_open | YES | steering bushings - steering linkage bush set | 1
Wire rework - Split overlength heavy feed wire into 3 serviceable segments | 3 segments | Electrical workshop service (rework existing wires) | Yes | PKR 3000-12000 (labor + lugs/heat-shrink re-termination) | images/20260411_065030.jpg | WORKSHOP_TASK | Cut+terminate+heat-shrink+continuity/voltage-drop test | 20260411_065030.jpg;20260321_235600.jpg | Electrical_Master | Yes. Rework existing overlength cable by cutting into 3 segments and re-terminating. | DONE_VERIFY_INSTALL | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | DONE_VERIFY_INSTALL |  |  | COMPLETED_ON_HAND | Task completed: 25mm² main feed split into 3 segments | 2026-04-16 | Included in market work (cost not logged yet) | PWR-04/PWR-05/PWR-06 split done as planned. Recheck crimp quality + continuity before final install. | 3000 | 12000 | 7500 | no |  | NO | wire rework - split overlength heavy feed wire into 3 serviceable segments | 1
Electrical tape (automotive PVC, 19mm x 18-20m) | 10 rolls | New electrical market (not donor car) | No | PKR 1500-4500 | images/20260411_065030.jpg | BUY_NOW | Good adhesive and heat tolerance, not brittle PVC | 20260411_065030.jpg | SUB-17 | N/A consumable item; buy new. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | Standard consumable; online purchase is fine. | https://www.daraz.pk/catalog/?q=electrical+tape+19mm | BUY_NOW | https://www.daraz.pk/catalog/?q=electrical+tape+19mm | https://www.ubuy.com.pk/en/search/index/view/product/B0B5VQW6XK/s/3m-electrical-tape-19mm/store/store | NOT_PURCHASED |  |  |  |  | 1500 | 4500 | 3000 | no |  | YES | electrical tape (automotive pvc, 19mm x 18-20m) | 1
Cloth harness loom tape (Tesa-style) | 5 rolls | New electrical market (not donor car) | No | PKR 2500-9000 | images/20260411_065030.jpg | BUY_NOW | Automotive-grade cloth tape; abrasion and heat resistance | 20260411_065030.jpg | SUB-23 | N/A consumable item; buy new. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | Standard consumable; online purchase is fine. | https://www.daraz.pk/products/19mmx15m-universal-heat-resistant-nap-adhesive-cloth-electrical-automotive-tape-i281397325.html | BUY_NOW | https://www.daraz.pk/products/19mmx15m-universal-heat-resistant-nap-adhesive-cloth-electrical-automotive-tape-i281397325.html | https://www.daraz.pk/catalog/?q=automotive+cloth+harness+tape | NOT_PURCHASED |  |  |  |  | 2500 | 9000 | 5750 | no |  | YES | cloth harness loom tape (tesa-style) | 1
Firewall grommet assortment | 1 kit | New electrical market (not donor car) | Yes | PKR 2000-7000 | images/20260411_143135.jpg | BUY_NOW | Hole ID/OD fit and thickness for firewall panels | 20260411_143135.jpg | SUB-11 | N/A consumable item; buy new. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | Standard consumable; online purchase is fine. | https://www.daraz.pk/catalog/?q=firewall+grommet+assortment | BUY_NOW | https://www.daraz.pk/catalog/?q=firewall+grommet+assortment | https://www.ubuy.com.pk/en/product/F3KO60UI-swpeet-246pcs-sae-metric-grease-nipple-assortment-kit-hydraulic-grease-fittings-standard-with-plasti | NOT_PURCHASED |  |  |  |  | 2000 | 7000 | 4500 | no |  | YES | firewall grommet assortment | 1
EPS donor candidate - Toyota Prius column assist set (complete kit) | 1 complete kit | Toyota donor car (Bilal Ganj) | Yes | PKR 60000-150000 | images/20260321_235600.jpg | QUOTE_ONLY | Motor smooth assist, ECU + shafts + U-joints + couplers + brackets + pigtails included | 20260321_235600.jpg;20260406_031010.jpg | 229-C1 | N/A candidate option. Buy only if complete kit passes mechanic inspection and fit checks. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 60000 | 150000 | 105000 | no |  | YES | eps donor candidate - toyota prius column assist set (complete kit) | 1
EPS donor candidate - Toyota Corolla/Axio column assist set (complete kit) | 1 complete kit | Toyota donor car (Bilal Ganj) | Yes | PKR 55000-140000 | images/20260321_235600.jpg | QUOTE_ONLY | No lash/noise, compatible column length, complete ECU/connectors/shafts | 20260321_235600.jpg;20260406_031010.jpg | 229-C2 | N/A candidate option. Buy only if complete kit passes mechanic inspection and fit checks. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 55000 | 140000 | 97500 | no |  | YES | eps donor candidate - toyota corolla/axio column assist set (complete kit) | 1
EPS donor candidate - Toyota Vitz/Yaris column assist set (complete kit) | 1 complete kit | Toyota donor car (Bilal Ganj) | Yes | PKR 50000-130000 | images/20260321_235600.jpg | QUOTE_ONLY | Column mount and spline compatibility; complete wiring pigtails and couplers | 20260321_235600.jpg;20260406_031010.jpg | 229-C3 | N/A candidate option. Buy only if complete kit passes mechanic inspection and fit checks. | AS_LISTED | Unchanged from active parts list. | KEPT_IN_ACTIVE | No change. |  | KEEP_AS_ACTIVE |  |  | NOT_PURCHASED |  |  |  |  | 50000 | 130000 | 90000 | no |  | YES | eps donor candidate - toyota vitz/yaris column assist set (complete kit) | 1
Rear anti-inversion kit - FK08 (spring flip prevention) | 1 kit | OME/EMU supplier or suspension fabricator | Yes | PKR 12000-35000 | images/20260411_220214.jpg | CONDITIONAL_LOCAL_ACTIVE | Bracket geometry for your rear spring setup and axle travel clearance | 20260411_220214.jpg | SUS-10 | Maybe. If current rear springs show no inversion tendency, can defer this item. | BUY_ONLY_IF_INVERSION_RISK | Only needed if spring inversion tendency appears. | KEPT_IN_ACTIVE | Buy only if rear inversion tendency appears after spring setup. | https://www.pakwheels.com/accessories-spare-parts/search/-/ct_steering-suspension/ | CONDITIONAL | https://www.pakwheels.com/accessories-spare-parts/search/-/ct_steering-suspension/ |  | NOT_PURCHASED |  |  |  |  | 12000 | 35000 | 23500 | no |  | YES | rear anti-inversion kit - fk08 (spring flip prevention) | 1
Shock absorbers (new genuine, Pakistan high-quality path) | 1 full set (front+rear) | Agriauto genuine shocks (KYB/Gabriel global standards), authorized dealer network | Yes | PKR 25,000-80,000 (quote by exact model fitment) | images/20260324_004852.jpg | QUOTE_THEN_BUY_ACTIVE | Exact fitment length/mount type, new genuine packaging, invoice/warranty | 20260324_004852.jpg;20260411_220207.jpg | SUS-11 | Maybe. Replace if damping is weak, leaking, or ride control is poor. | QUOTE_FIRST_THEN_BUY | Added to active suspension quality plan. | KEPT_IN_ACTIVE | Best locally verifiable quality path is Agriauto genuine shocks (KYB/Gabriel standards, OEM-linked, 6-month warranty statement). | https://www.agriauto.com.pk/about-us/ ; https://www.agriauto.com.pk/products-post/genuine/ ; https://www.agriauto.com.pk/products-post/shock-absorbers-and-struts/ | ACTIVE_SUSPENSION_CORE_ORDER_NEW | https://www.agriauto.com.pk/distributors-network/ | https://www.agriauto.com.pk/products-post/shock-absorbers-and-struts/ | NOT_PURCHASED |  |  |  |  | 25000 | 80000 | 52500 | no |  | YES | shock absorbers (new genuine, pakistan high-quality path) | 1
Split corrugated wire conduit / outer protective hosing | As purchased (exact length to confirm) | Local electrical market | No | PKR 1,000-6,000 | /var/folders/2r/rbnydbl91t9_jcjfhssspzqw0000gn/T/ai-chat-attachment-12067298280348876343.png | BUY_NOW_ACTIVE | Correct ID for loom branches, heat tolerance, abrasion resistance | ai-chat-attachment-12067298280348876343.png | ELEC-LOOM-01 | N/A new consumable. | PROCURED_ON_HAND | Added from user market purchase update. | KEPT_IN_ACTIVE | Use split conduit on exposed runs; cloth tape for cabin bundles. |  | PROCURED_ON_HAND |  |  | PROCURED_ON_HAND | Purchased (length not yet logged) | 2026-04-16 | Not logged | Bought during market visit. | 1000 | 6000 | 3500 | no |  | NO | split corrugated wire conduit / outer protective hosing | 1
Booster/charging cable set (MAXXIS Booster Cable 1000 AMP) | 1 set | Local electrical market | No | PKR 2,000-10,000 | /var/folders/2r/rbnydbl91t9_jcjfhssspzqw0000gn/T/ai-chat-attachment-8920882528865792364.png | BUY_NOW_ACTIVE | Clamp quality, copper content, cable gauge, insulation flexibility | ai-chat-attachment-8920882528865792364.png | ELEC-CHG-01 | Useful workshop support item. | PROCURED_ON_HAND | Added from user market purchase update. | KEPT_IN_ACTIVE | Use as workshop support; not a substitute for permanent vehicle main feeds. |  | PROCURED_ON_HAND |  |  | PROCURED_ON_HAND | 1 set purchased | 2026-04-16 | Not logged | Bought during market visit. | 2000 | 10000 | 6000 | no |  | NO | booster/charging cable set (maxxis booster cable 1000 amp) | 1
Battery terminal clamps / terminators (pair) | 2 terminals | Local electrical market | Yes | PKR 500-3,000 | /var/folders/2r/rbnydbl91t9_jcjfhssspzqw0000gn/T/ai-chat-attachment-4151165269365336421.png | BUY_NOW_ACTIVE | Clamp fit on battery posts, material quality, corrosion resistance | ai-chat-attachment-4151165269365336421.png;ai-chat-attachment-14089458610305842598.png | ELEC-BAT-TERM-01 | New terminals are preferred if old ones are worn/oxidized. | PROCURED_ON_HAND_VERIFY_FIT | Added from user market purchase update. | KEPT_IN_ACTIVE | Use anti-corrosion paste and correct clamp torque at install. |  | PROCURED_ON_HAND_VERIFY_FIT |  |  | PROCURED_ON_HAND_VERIFY_FIT | 2 terminals purchased | 2026-04-16 | Not logged | Bought during market visit. | 500 | 3000 | 1750 | no |  | NO | battery terminal clamps / terminators (pair) | 1

## SUSPENSION_HOLD_MISMATCH
item | quantity | likely source if from another car | needs mechanic checked | expected price | image to show | purchase stage | what to verify | all image refs | source row | existing one ok? (analysis) | buy_decision_now | cleanup_reason | cleanup_action | pakistan_quality_recommendation | verified_source_url | decision_today | primary_purchase_link | backup_purchase_link | procurement_status | purchased_qty | purchased_on | purchased_est_cost_pkr | purchase_notes | price_min_pkr | price_max_pkr | price_mid_pkr | parts_tab_procured | parts_tab_status_hint | include_in_remaining_budget | dedup_key | duplicate_count
OME/EMU front shock pair - OME-60097 x2 | 2 shocks (1 front pair) | OME/EMU importer or off-road parts supplier (new genuine preferred) | Yes | PKR 55000-110000 | images/20260324_004852.jpg | QUOTE_ONLY | Part number stamping OME-60097, eye/bush size, compressed/extended length, genuine packaging | 20260324_004852.jpg;20260411_220207.jpg | 33-A | N/A optional upgrade. Existing suspension can be retained if serviceable and ride goals are acceptable. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 55000 | 110000 | 82500 |  | HOLD tab | NO | ome/emu front shock pair - ome-60097 x2 | 1
OME/EMU rear shock pair - OME-63064 x2 | 2 shocks (1 rear pair) | OME/EMU importer or off-road parts supplier (new genuine preferred) | Yes | PKR 55000-110000 | images/20260324_004852.jpg | QUOTE_ONLY | Part number stamping OME-63064, eye/bush size, compressed/extended length, genuine packaging | 20260324_004852.jpg;20260411_220207.jpg | 33-B | N/A optional upgrade. Existing suspension can be retained if serviceable and ride goals are acceptable. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 55000 | 110000 | 82500 |  | HOLD tab | NO | ome/emu rear shock pair - ome-63064 x2 | 1
OME greasable shackle front (grease-injection pin type) - OMEGS8 (front, pre-1980/15mm pin note) | 1 kit | OME/EMU importer or off-road parts supplier (new genuine preferred) | Yes | PKR 25000-60000 | images/20260411_220207.jpg | QUOTE_ONLY | Confirm pin dia and compatibility; verify grease channel and zerk ports are present | 20260411_220207.jpg | 44 | N/A optional upgrade. Existing shackles can stay if not worn; greasable set improves serviceability. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 25000 | 60000 | 42500 |  | HOLD tab | NO | ome greasable shackle front (grease-injection pin type) - omegs8 (front, pre-1980/15mm pin note) | 1
OME greasable shackle rear (grease-injection pin type) - OMEGS9 (rear) | 1 kit | OME/EMU importer or off-road parts supplier (new genuine preferred) | Yes | PKR 25000-65000 | images/20260411_220214.jpg | QUOTE_ONLY | Confirm pin dia and compatibility; verify grease channel and zerk ports are present | 20260411_220214.jpg | 45 | N/A optional upgrade. Existing shackles can stay if play is acceptable; greasable set improves serviceability. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 25000 | 65000 | 45000 |  | HOLD tab | NO | ome greasable shackle rear (grease-injection pin type) - omegs9 (rear) | 1
OME bush kit - OMESB30 | 4 kits | OME/EMU importer or off-road parts supplier (new genuine preferred) | Yes | PKR 28000-60000 | images/20260324_004852.jpg | QUOTE_ONLY | Confirm bush count per spring-eye set | 20260324_004852.jpg | 46 | N/A optional upgrade. Existing suspension can be retained if serviceable and ride goals are acceptable. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 28000 | 60000 | 44000 |  | HOLD tab | NO | ome bush kit - omesb30 | 1
OME U-bolt kit - OMEU59A | 7 kits | OME/EMU importer or off-road parts supplier (new genuine preferred) | Yes | PKR 42000-98000 | images/20260411_220207.jpg | QUOTE_ONLY | Confirm rod dia, width, leg length, pitch | 20260411_220207.jpg | 47 | N/A optional upgrade. Existing suspension can be retained if serviceable and ride goals are acceptable. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 42000 | 98000 | 70000 |  | HOLD tab | NO | ome u-bolt kit - omeu59a | 1
Grease-injection fittings kit (zerk nipples + dust caps) for greasable shackles | 1 kit (8-12 nipples + caps) | New suspension hardware shop (not donor) | Yes | PKR 1000-4500 | images/20260411_220207.jpg | QUOTE_ONLY | Thread pitch fit on shackle pins, grease gun coupler fit, no damaged threads | 20260411_220207.jpg;20260411_220214.jpg | 44/45-SUP | Maybe. If shackle kit includes good nipples/caps, separate buy not needed. | DO_NOT_BUY_NOW | Alternative OME/EMU path; mismatch risk vs current local leaf-spring active plan. | MOVED_TO_HOLD | Hold this branch unless you decide to move from local-spring active path to premium OME branch with new genuine proof only. | https://www.arb.com.au/stores/arb-usa/ | HOLD_DO_NOT_BUY | HOLD (do not order now) | [6 empty] | 1000 | 4500 | 2750 |  | HOLD tab | NO | grease-injection fittings kit (zerk nipples + dust caps) for greasable shackles | 1

## HARDWARE_REMAINING_DEDUP
item | quantity | source_rows | expected_price | price_min_pkr | price_max_pkr | price_mid_pkr | parts_tab_procured | status | notes
Body mount rubber - OEM-style body mount insulator set | Full set | 12 | PKR 15000-60000 | 15000 | 60000 | 37500 | no | NOT_PURCHASED | AS_LISTED
Cloth harness loom tape (Tesa-style) | 5 rolls | SUB-23 | PKR 2500-9000 | 2500 | 9000 | 5750 | no | NOT_PURCHASED | AS_LISTED
Electrical tape (automotive PVC, 19mm x 18-20m) | 10 rolls | SUB-17 | PKR 1500-4500 | 1500 | 4500 | 3000 | no | NOT_PURCHASED | AS_LISTED
Firewall grommet assortment | 1 kit | SUB-11 | PKR 2000-7000 | 2000 | 7000 | 4500 | no | NOT_PURCHASED | AS_LISTED
Fuse box - Compact covered ATO/ATC fuse block 6-way | 3 identical | 186 | PKR 11100-21000 | 11100 | 21000 | 16050 | no | NOT_PURCHASED | AS_LISTED
Heat plugs / glow plugs - Diesel glow plug set (thread/reach/voltage per engine code) | Full set | 29 | PKR 12000-36000 | 12000 | 36000 | 24000 | no | NOT_PURCHASED | AS_LISTED
Kit A nut - M10 nyloc/all-metal mix | 24 (+20% spare) | 244 | PKR 1200-2400 | 1200 | 2400 | 1800 | no | NOT_PURCHASED | AS_LISTED
Kit A nut - M12 nut | 6 (+20% spare) | 244 | PKR 500-1100 | 500 | 1100 | 800 | no | NOT_PURCHASED | AS_LISTED
Kit A sleeve/spacer - Sleeve for M10 mount points | 16 | 244 | PKR 1200-3200 | 1200 | 3200 | 2200 | no | NOT_PURCHASED | AS_LISTED
Kit A spring washer - M10 spring washer | 20 (+20% spare) | 244 | PKR 300-650 | 300 | 650 | 475 | no | NOT_PURCHASED | AS_LISTED
Kit A spring washer - M12 spring washer | 6 (+20% spare) | 244 | PKR 150-350 | 150 | 350 | 250 | no | NOT_PURCHASED | AS_LISTED
Kit A washer - M10 flat washer | 40 (+20% spare) | 244 | PKR 400-900 | 400 | 900 | 650 | no | NOT_PURCHASED | AS_LISTED
Kit A washer - M12 flat washer | 12 (+20% spare) | 244 | PKR 200-500 | 200 | 500 | 350 | no | NOT_PURCHASED | AS_LISTED
Kit B bolt - M6x1.0 class 8.8 hex bolts lengths 12/16/20/25mm | 220 total | 245 | PKR 6000-13000 | 6000 | 13000 | 9500 | no | NOT_PURCHASED | AS_LISTED
Kit B bolt - M8x1.25 class 8.8 bolts lengths 16/20/25/30mm | 120 total | 245 | PKR 4800-10800 | 4800 | 10800 | 7800 | no | NOT_PURCHASED | AS_LISTED
Kit B nuts - M6 flange nuts | 80 | 245 | PKR 1200-2800 | 1200 | 2800 | 2000 | no | NOT_PURCHASED | AS_LISTED
Kit B nuts - M6 nyloc | 160 | 245 | PKR 3200-6400 | 3200 | 6400 | 4800 | no | NOT_PURCHASED | AS_LISTED
Kit B nuts - M8 flange nuts | 40 | 245 | PKR 1000-2200 | 1000 | 2200 | 1600 | no | NOT_PURCHASED | AS_LISTED
Kit B nuts - M8 nyloc | 90 | 245 | PKR 2700-6300 | 2700 | 6300 | 4500 | no | NOT_PURCHASED | AS_LISTED
Kit B spring washers - M6 spring washers | 140 | 245 | PKR 600-1700 | 600 | 1700 | 1150 | no | NOT_PURCHASED | AS_LISTED
Kit B spring washers - M8 spring washers | 90 | 245 | PKR 600-1600 | 600 | 1600 | 1100 | no | NOT_PURCHASED | AS_LISTED
Kit B washers - M6 flat washers | 300 | 245 | PKR 900-2400 | 900 | 2400 | 1650 | no | NOT_PURCHASED | AS_LISTED
Kit B washers - M8 flat washers | 180 | 245 | PKR 900-2500 | 900 | 2500 | 1700 | no | NOT_PURCHASED | AS_LISTED
Kit C captive nut - M6 captive/clip nuts | 120 | 246 | PKR 1800-4200 | 1800 | 4200 | 3000 | no | NOT_PURCHASED | AS_LISTED
Kit C captive nut - M8 captive/clip nuts | 60 | 246 | PKR 1500-3300 | 1500 | 3300 | 2400 | no | NOT_PURCHASED | AS_LISTED
Kit C rivnut - M6 steel rivnuts | 30 | 246 | PKR 900-2100 | 900 | 2100 | 1500 | no | NOT_PURCHASED | AS_LISTED
Kit C rivnut - M8 steel rivnuts | 20 | 246 | PKR 900-2200 | 900 | 2200 | 1550 | no | NOT_PURCHASED | AS_LISTED
Kit C weld nut - M6 weld nuts | 30 | 246 | PKR 600-1500 | 600 | 1500 | 1050 | no | NOT_PURCHASED | AS_LISTED
Kit C weld nut - M8 weld nuts | 20 | 246 | PKR 700-1600 | 700 | 1600 | 1150 | no | NOT_PURCHASED | AS_LISTED
Kit D flange nut - M6 serrated flange nut | 40 | 247 | PKR 800-1800 | 800 | 1800 | 1300 | no | NOT_PURCHASED | AS_LISTED
Kit D flange nut - M8 serrated flange nut | 20 | 247 | PKR 700-1500 | 700 | 1500 | 1100 | no | NOT_PURCHASED | AS_LISTED
Kit D star washer - M10 star/serrated washer | 40 | 247 | PKR 700-1700 | 700 | 1700 | 1200 | no | NOT_PURCHASED | AS_LISTED
Kit D star washer - M6 star/serrated washer | 120 | 247 | PKR 700-1800 | 700 | 1800 | 1250 | no | NOT_PURCHASED | AS_LISTED
Kit D star washer - M8 star/serrated washer | 80 | 247 | PKR 800-2200 | 800 | 2200 | 1500 | no | NOT_PURCHASED | AS_LISTED
Local front leaf spring pack (new, custom to measured dimensions) | 2 packs | 15 | PKR 35000-90000 | 35000 | 90000 | 62500 | no | NOT_PURCHASED | MEASURE_FIRST_THEN_BUY
Local rear leaf spring pack (new, custom to measured dimensions) | 2 packs | 16 | PKR 35000-90000 | 35000 | 90000 | 62500 | no | NOT_PURCHASED | MEASURE_FIRST_THEN_BUY
Rear anti-inversion kit - FK08 (spring flip prevention) | 1 kit | SUS-10 | PKR 12000-35000 | 12000 | 35000 | 23500 | no | NOT_PURCHASED | BUY_ONLY_IF_INVERSION_RISK
Shims/spacers - M10/M12 shim pack thickness 1/2/3/5mm | Assorted full pack | 13 | PKR 3000-12000 | 3000 | 12000 | 7500 | no | NOT_PURCHASED | AS_LISTED
Shock absorbers (new genuine, Pakistan high-quality path) | 1 full set (front+rear) | SUS-11 | PKR 25,000-80,000 (quote by exact model fitment) | 25000 | 80000 | 52500 | no | NOT_PURCHASED | QUOTE_FIRST_THEN_BUY
Steering bushings - Steering linkage bush set | 1 set | 230 | PKR 3000-12000 | 3000 | 12000 | 7500 | no | NOT_PURCHASED | BUY_ONLY_IF_PLAY_FOUND
TOTAL